## HELP Calls Report
Helpcall Code | Site Description | Created Date | Building Description | Description | Logged Date | Logged Time | Category Description | Priority | Priority Colour | Priority Description | Target Complete Date | Actual Respond Time | Target Complete Time | Actual Complete Date | Supplier Name
HLP095726 | GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) | 12/06/2024 | GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) - MAIN BUILDING | Engineer needed to replace a full size slab which has broken in 2 pieces at the back of the building on top of a small wall or seating area. if someone stepped or sat on this and is unaware that there is no support underneath it it and will fall through and can cause an injury. Photos attached. I am available in the building Monday to Thursday 8am until 1:15pm and on Fridays 12pm until 5:15pm. This is external so access anytime will be possible. | 12/06/2024 | 12:26 | Reactive Repair | D | Green | Routine - 2 day response | 19/06/2024 | 12:37 | 17:00 | 2024-06-14 | Skanska
HLP100004 | GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) | 04/09/2024 | GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) - MAIN BUILDING | Path from Gate 55 to Wester Hailes Road broken up by sections of green fencing are either sunken down or sticking upwards due to uneven ground below in both cases. 14 to 17 slabs are like this including 4 at front entrance of building. Photos attached. Engineer needed to repair due to size of task 2 weeks have been given to complete and a week to respond. Staff times on staff: Monday – Thursday 8am – 9pm; Friday 10am – 5pm; Saturday 10am – 2pm. Contact XXXX on XXXX though works are external or see Facilities staff onsite. | 04/09/2024 | 14:41 | Reactive Repair | D | Green | Routine - 2 day response | 26/09/2024 | 08:00 | 17:00 | 2024-09-09 | Skanska
HLP100099 | GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) | 05/09/2024 | GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) - MAIN BUILDING | contractor to attend to inspect and make good the paving slabs and steps on the top of the pathway leading to Wester Hailes road. These are uneven. Please see the attached photo | 05/09/2024 | 14:07 | Reactive Repair | D | Green | Routine - 2 day response | 12/09/2024 | 08:00 | 14:07 | 2024-09-06 | Skanska
HLP105968 | GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) | 18/12/2024 | GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) - MAIN BUILDING | Per XXXX Fabric Surveyor - Works Description - Slabbing and dwarf retaining wall repairs Detailed Description - Works to area 2 only; as marked red on attached site plan: 1. Carefully rake out all vegetation; allow for bagging and removal off site – see picture reference No.3 to 5. 2. Repoint open joints to paving slabs; cement mortar (1:4). 3. Precast paving slabs 600x900x50mm: Lift and relay only where uneven/raised areas; repoint on completion; cement mortar(1:4) 4. Allow for replacing cracked/damaged only slabs only; as required. Works to area 3 only; as marked orange attached site plan – see picture reference No.6 to 8. 5. Carefully rake out vegetation; allow for bagging and removal off site 6. Repoint open joints of paving slabs and steps in cement mortar (1:4). 7. Re-bed all loose/unsecure paving slabs to dwarf retaining wall in cement mortar (1:4). 8. Point paving slabs on completion; cement mortar (1:4). 9. Point brickwork to retaining wall; cement mortar (1:4). Location of works - Area 2 and 3 of attached picture schedule . Call Priority - Priority E Value - £3500.00 Completion date and duration of works discussed and agreed with January 24th 2025 | 18/12/2024 | 09:30 | Reactive Repair | E | Green | Priority E - Ad-hoc User Defined Response / Rectification | 24/01/2025 | 08:00 | 17:00 | 2025-02-12 | Skanska
Report: HLP01: Help Call
Filtering details:
Code Multiple Values 'HLP095726,HLP100004,HLP100099,HLP105968', Site Matches 'SIT0976', Building Includes 'BLD01805'
Ordering details:
`Helpcall Code` (ascending)
Rows returned:
Returned 4 rows (from 1 to 4) of 114355 rows.

## HLP105968 - emails
Email Date | Module | Record Description | Email Message
18/12/2024 09:34:17 | Help Call | Per XXXX Fabric Surveyor - Works Description - Slabbing and dwarf retaining wall repairs Detailed Description - Works to area 2 only; as marked red on attached site plan: 1. Carefully rake out all vegetation; allow for bagging and removal off site – see picture reference No.3 to 5. 2. Repoint open joints to paving slabs; cement mortar (1:4). 3. Precast paving slabs 600x900x50mm: Lift and relay only where uneven/raised areas; repoint on completion; cement mortar(1:4) 4. Allow for replacing cracked/damaged only slabs only; as required. Works to area 3 only; as marked orange attached site plan – see picture reference No.6 to 8. 5. Carefully rake out vegetation; allow for bagging and removal off site 6. Repoint open joints of paving slabs and steps in cement mortar (1:4). 7. Re-bed all loose/unsecure paving slabs to dwarf retaining wall in cement mortar (1:4). 8. Point paving slabs on completion; cement mortar (1:4). 9. Point brickwork to retaining wall; cement mortar (1:4). Location of works - Area 2 and 3 of attached picture schedule . Call Priority - Priority E Value - £3500.00 Completion date and duration of works discussed and agreed with January 24th 2025 | Thank you for your service request to the Corporate Property FM Help Desk. Your reference for this call is HLP105968. Service Request details: Priority: E - Priority E - Ad-hoc User Defined Response / Rectification Site: SIT0976 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) BLD01805 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) - MAIN BUILDING Description: Per XXXX Fabric Surveyor - Works Description - Slabbing and dwarf retaining wall repairs Detailed Description - Works to area 2 only; as marked red on attached site plan: 1. Carefully rake out all vegetation; allow for bagging and removal off site – see picture reference No.3 to 5. 2. Repoint open joints to paving slabs; cement mortar (1:4). 3. Precast paving slabs 600x900x50mm: Lift and relay only where uneven/raised areas; repoint on completion; cement mortar(1:4) 4. Allow for replacing cracked/damaged only slabs only; as required. Works to area 3 only; as marked orange attached site plan – see picture reference No.6 to 8. 5. Carefully rake out vegetation; allow for bagging and removal off site 6. Repoint open joints of paving slabs and steps in cement mortar (1:4). 7. Re-bed all loose/unsecure paving slabs to dwarf retaining wall in cement mortar (1:4). 8. Point paving slabs on completion; cement mortar (1:4). 9. Point brickwork to retaining wall; cement mortar (1:4). Location of works - Area 2 and 3 of attached picture schedule . Call Priority - Priority E Value - £3500.00 Completion date and duration of works discussed and agreed with January 24th 2025 _____________________________________________________________ The Facilities Management Helpdesk is run by our dedicated customer services team. You can contact the FM Helpdesk either by: Email: corporateproperty.helpdesk@edinburgh.gov.uk Telephone: 0131 529 7878
18/12/2024 10:32:05 | Help Call | Per XXXX Fabric Surveyor - Works Description - Slabbing and dwarf retaining wall repairs Detailed Description - Works to area 2 only; as marked red on attached site plan: 1. Carefully rake out all vegetation; allow for bagging and removal off site – see picture reference No.3 to 5. 2. Repoint open joints to paving slabs; cement mortar (1:4). 3. Precast paving slabs 600x900x50mm: Lift and relay only where uneven/raised areas; repoint on completion; cement mortar(1:4) 4. Allow for replacing cracked/damaged only slabs only; as required. Works to area 3 only; as marked orange attached site plan – see picture reference No.6 to 8. 5. Carefully rake out vegetation; allow for bagging and removal off site 6. Repoint open joints of paving slabs and steps in cement mortar (1:4). 7. Re-bed all loose/unsecure paving slabs to dwarf retaining wall in cement mortar (1:4). 8. Point paving slabs on completion; cement mortar (1:4). 9. Point brickwork to retaining wall; cement mortar (1:4). Location of works - Area 2 and 3 of attached picture schedule . Call Priority - Priority E Value - £3500.00 Completion date and duration of works discussed and agreed with January 24th 2025 | Dear XXXX , Your helpdesk call HLP105968 has now been issued. R - Reactive Repair SIT0976 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) BLD01805 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) - MAIN BUILDING Per XXXX Fabric Surveyor - Works Description - Slabbing and dwarf retaining wall repairs Detailed Description - Works to area 2 only; as marked red on attached site plan: 1. Carefully rake out all vegetation; allow for bagging and removal off site – see picture reference No.3 to 5. 2. Repoint open joints to paving slabs; cement mortar (1:4). 3. Precast paving slabs 600x900x50mm: Lift and relay only where uneven/raised areas; repoint on completion; cement mortar(1:4) 4. Allow for replacing cracked/damaged only slabs only; as required. Works to area 3 only; as marked orange attached site plan – see picture reference No.6 to 8. 5. Carefully rake out vegetation; allow for bagging and removal off site 6. Repoint open joints of paving slabs and steps in cement mortar (1:4). 7. Re-bed all loose/unsecure paving slabs to dwarf retaining wall in cement mortar (1:4). 8. Point paving slabs on completion; cement mortar (1:4). 9. Point brickwork to retaining wall; cement mortar (1:4). Location of works - Area 2 and 3 of attached picture schedule . Call Priority - Priority E Value - £3500.00 Completion date and duration of works discussed and agreed with January 24th 2025 Many thanks FM Helpdesk

## HLP100099 - emails
Email Date | Module | Record Description | Email Message
05/09/2024 14:16:06 | Help Call | contractor to attend to inspect and make good the paving slabs and steps on the top of the pathway leading to Wester Hailes road. These are uneven. Please see the attached photo | Thank you for your service request to the Corporate Property FM Help Desk. Your reference for this call is HLP100099. Service Request details: Priority: D - Routine - 2 day response Site: SIT0976 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) BLD01805 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) - MAIN BUILDING Description: contractor to attend to inspect and make good the paving slabs and steps on the top of the pathway leading to Wester Hailes road. These are uneven. Please see the attached photo _____________________________________________________________ The Facilities Management Helpdesk is run by our dedicated customer services team. You can contact the FM Helpdesk either by: Email: corporateproperty.helpdesk@edinburgh.gov.uk Telephone: 0131 529 7878
05/09/2024 14:26:05 | Help Call | contractor to attend to inspect and make good the paving slabs and steps on the top of the pathway leading to Wester Hailes road. These are uneven. Please see the attached photo | Dear XXXX , Your helpdesk call HLP100099 has now been issued. R - Reactive Repair SIT0976 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) BLD01805 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) - MAIN BUILDING contractor to attend to inspect and make good the paving slabs and steps on the top of the pathway leading to Wester Hailes road. These are uneven. Please see the attached photo Many thanks FM Helpdesk

## HLP100004 - emails
Email Date | Module | Record Description | Email Message
04/09/2024 14:46:05 | Help Call | Path from Gate 55 to Wester Hailes Road broken up by sections of green fencing are either sunken down or sticking upwards due to uneven ground below in both cases. 14 to 17 slabs are like this including 4 at front entrance of building. Photos attached. Engineer needed to repair due to size of task 2 weeks have been given to complete and a week to respond. Staff times on staff: Monday – Thursday 8am – 9pm; Friday 10am – 5pm; Saturday 10am – 2pm. Contact XXXX on XXXX though works are external or see Facilities staff onsite. | Thank you for your service request to the Corporate Property FM Help Desk. Your reference for this call is HLP100004. Service Request details: Priority: D - Routine - 2 day response Site: SIT0976 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) BLD01805 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) - MAIN BUILDING Description: Path from Gate 55 to Wester Hailes Road broken up by sections of green fencing are either sunken down or sticking upwards due to uneven ground below in both cases. 14 to 17 slabs are like this including 4 at front entrance of building. Photos attached. Engineer needed to repair due to size of task 2 weeks have been given to complete and a week to respond. Staff times on staff: Monday – Thursday 8am – 9pm; Friday 10am – 5pm; Saturday 10am – 2pm. Contact Laura Vinas Boreland on 01315295667 though works are external or see Facilities staff onsite. _____________________________________________________________ The Facilities Management Helpdesk is run by our dedicated customer services team. You can contact the FM Helpdesk either by: Email: corporateproperty.helpdesk@edinburgh.gov.uk Telephone: 0131 529 7878
04/09/2024 17:56:14 | Help Call | Path from Gate 55 to Wester Hailes Road broken up by sections of green fencing are either sunken down or sticking upwards due to uneven ground below in both cases. 14 to 17 slabs are like this including 4 at front entrance of building. Photos attached. Engineer needed to repair due to size of task 2 weeks have been given to complete and a week to respond. Staff times on staff: Monday – Thursday 8am – 9pm; Friday 10am – 5pm; Saturday 10am – 2pm. Contact XXXX on XXXX though works are external or see Facilities staff onsite. | Dear XXXX , Your helpdesk call HLP100004 has now been issued. R - Reactive Repair SIT0976 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) BLD01805 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) - MAIN BUILDING Path from Gate 55 to Wester Hailes Road broken up by sections of green fencing are either sunken down or sticking upwards due to uneven ground below in both cases. 14 to 17 slabs are like this including 4 at front entrance of building. Photos attached. Engineer needed to repair due to size of task 2 weeks have been given to complete and a week to respond. Staff times on staff: Monday – Thursday 8am – 9pm; Friday 10am – 5pm; Saturday 10am – 2pm. Contact Laura Vinas Boreland on 01315295667 though works are external or see Facilities staff onsite. Many thanks FM Helpdesk

## HLP095726 - emails
Email Date | Module | Record Description | Email Message
12/06/2024 12:28:30 | Help Call | Engineer needed to replace a full size slab which has broken in 2 pieces at the back of the building on top of a small wall or seating area. if someone stepped or sat on this and is unaware that there is no support underneath it it and will fall through and can cause an injury. Photos attached. I am available in the building Monday to Thursday 8am until 1:15pm and on Fridays 12pm until 5:15pm. This is external so access anytime will be possible. | Thank you for your service request to the Corporate Property FM Help Desk. Your reference for this call is HLP095726. Service Request details: Priority: D - Routine - 2 day response Site: SIT0976 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) BLD01805 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) - MAIN BUILDING Description: Engineer needed to replace a full size slab which has broken in 2 pieces at the back of the building on top of a small wall or seating area. if someone stepped or sat on this and is unaware that there is no support underneath it it and will fall through and can cause an injury. Photos attached. I am available in the building Monday to Thursday 8am until 1:15pm and on Fridays 12pm until 5:15pm. This is external so access anytime will be possible. _____________________________________________________________ The Facilities Management Helpdesk is run by our dedicated customer services team. You can contact the FM Helpdesk either by: Email: corporateproperty.helpdesk@edinburgh.gov.uk Telephone: 0131 529 7878
12/06/2024 12:32:33 | Help Call | Engineer needed to replace a full size slab which has broken in 2 pieces at the back of the building on top of a small wall or seating area. if someone stepped or sat on this and is unaware that there is no support underneath it it and will fall through and can cause an injury. Photos attached. I am available in the building Monday to Thursday 8am until 1:15pm and on Fridays 12pm until 5:15pm. This is external so access anytime will be possible. | Dear Kevin Skimming , Your helpdesk call HLP095726 has now been issued. R - Reactive Repair SIT0976 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) BLD01805 - GATE 55 COMMUNITY CENTRE (SIGHTHILL LIBRARY AND COMMUNITY CENTRE) - MAIN BUILDING Engineer needed to replace a full size slab which has broken in 2 pieces at the back of the building on top of a small wall or seating area. if someone stepped or sat on this and is unaware that there is no support underneath it it and will fall through and can cause an injury. Photos attached. I am available in the building Monday to Thursday 8am until 1:15pm and on Fridays 12pm until 5:15pm. This is external so access anytime will be possible. Many thanks FM Helpdesk