## Activity20250821103824492
Phase Created | Road | Address 2 | Category | Activity Reference | Status | Start Date | End Date | Description | Auth | Local Ref | Location | Prom Organisation | Activity Att? | Latest Inspection Date
2025-08-07 14:35 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66710 | Awaiting Response | 2025-08-07 | 2025-08-07 | 2x double sky manhole covers sunken loose and noisy | City of Edinburgh Council | 3872109 | On Gorgie Road at junction with Mcleod Street. | City of Edinburgh Council | No | 2025-08-07 10:57
2025-08-06 18:32 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66707 | Denied | 2025-08-06 | 2025-08-06 | BT phone box has been damaged | City of Edinburgh Council | 3871385 | Outside the polish shop 364 Gorgie Road on footway | City of Edinburgh Council | No | 2025-08-06 14:52
2025-06-27 14:02 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66575 | Accepted | 2025-06-27 | 2025-06-27 | Double BT manhole loose and noisy on carriageway | City of Edinburgh Council | 3845714 | Coming off Balgreen Road left to Gorgie Road | City of Edinburgh Council | No | 2025-06-27 11:45
2025-06-27 13:45 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66574 | Accepted | 2025-06-27 | 2025-06-27 | Sunken and noisy BT manhole in c/way | City of Edinburgh Council | 3845693 | Outside Gorgie laundrette | City of Edinburgh Council | No | 2025-06-27 12:31
2025-06-13 17:16 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66526 | Denied | 2025-06-13 | 2025-06-13 | Manhole on footway collapsed. Made safe with cones | City of Edinburgh Council | 3836706 | Outside The Salvation Army, No's 254 to No. 256 | City of Edinburgh Council | No | 2025-06-13 10:00
2025-05-28 12:15 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66477 | Accepted | 2025-05-28 | 2025-05-28 | Vodafone double concrete manhole broken | City of Edinburgh Council | 3824591 | Outside 351 on footway | City of Edinburgh Council | No | 2025-05-28 09:17
2025-05-21 14:41 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66459 | Denied | 2025-05-21 | 2025-05-21 | Scottish Water Toby's raised above footway | City of Edinburgh Council | 3820281 | Outside 12 on footway | City of Edinburgh Council | No | 2025-05-21 10:31
2025-05-21 14:03 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66457 | Denied | 2025-05-21 | 2025-05-21 | Manhole sinking making footway uneven | City of Edinburgh Council | 3820205 | Outside 18 on footway | City of Edinburgh Council | No | 2025-05-21 10:29
2025-05-02 15:13 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66410 | Accepted | 2025-05-02 | 2025-05-02 | Loose and noisy BT cover on carriageway | City of Edinburgh Council | 3807958 | Outside 398 Gorgie Road, Spice of Asia | City of Edinburgh Council | No | 2025-05-01 11:08
2025-05-02 12:49 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66406 | Accepted | 2025-05-02 | 2025-05-02 | Manhole cover loose and noisy | City of Edinburgh Council | 3807752 | At traffic lights at the junction to Balgreen Road | City of Edinburgh Council | No | 2025-05-01 11:16
2025-04-16 09:43 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66343 | Accepted | 2025-04-16 | 2025-04-16 | Two double manhole covers (Norwood Telecom) low and noisy on carriageway. | City of Edinburgh Council | 3796916 | At junction with Robertson Avenue under rail bridge | City of Edinburgh Council | No | 2025-04-15 14:03
2025-04-16 09:24 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66342 | Accepted | 2025-04-16 | 2025-04-16 | Sunken cover on carriageway | City of Edinburgh Council | 3796884 | At junction with Robertson Avenue under rail bridge | City of Edinburgh Council | No | 2025-04-15 14:09
2025-03-17 16:01 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66210 | Accepted | 2025-03-17 | 2025-03-17 | Rocking and noisy manhole at pedestrian crossing in carriageway | City of Edinburgh Council | 3775766 | At Traffic lights at VPZ shop 193 Gorgie Road near to Wardlaw Place | City of Edinburgh Council | No | 2025-03-17 12:27
2025-02-18 14:34 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66094 | Denied | 2025-02-18 | 2025-02-18 | Damage to drainage Clay pipe causing subsidence on footway at manhole, made safe with walkboard. | City of Edinburgh Council | 3756514 | Outside Stratfords Bar from 227-229 Gorgie Road | City of Edinburgh Council | No | 2025-02-18 14:09
2025-02-07 13:17 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66066 | Accepted | 2025-02-07 | 2025-02-07 | Loose and noisy bt manhole on city bound carriageway | City of Edinburgh Council | 3749429 | Outside 352 Gorgie road | City of Edinburgh Council | No | 2025-02-06 10:26
2025-01-14 15:34 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65965 | Accepted | 2025-01-14 | 2025-01-14 | Sunken cover on footway at ductiles see pictures | City of Edinburgh Council | 3732436 | On the footway crossing at Murieston Road/dalry junction | City of Edinburgh Council | No | 2025-01-14 10:30
2025-01-09 16:04 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65950 | Denied | 2025-01-09 | 2025-01-09 | Scottish water sunken slabbed area around manhole | City of Edinburgh Council | 3729428 | Outside Stratford bar | City of Edinburgh Council | No | 2025-01-09 14:00
2024-12-20 13:33 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65899 | Denied | 2024-12-20 | 2024-12-20 | Sunken cover, damaged surround | City of Edinburgh Council | 3722886 | Between 387 and 389 | City of Edinburgh Council | No | 2024-12-18 13:22
2024-12-19 16:41 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65895 | Denied | 2024-12-19 | 2024-12-19 | Sunken cover, damaged surround | City of Edinburgh Council | 3722354 | Between 387 and 389 | City of Edinburgh Council | No | 2024-12-18 01:32
2024-12-19 16:02 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65892 | Accepted | 2024-12-19 | 2024-12-19 | Sunken cover, damaged surround | City of Edinburgh Council | 3722318 | Adjacent to 466 gorgie road | City of Edinburgh Council | No | 2024-12-18 13:20
2024-12-03 11:29 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65848 | Accepted | 2024-12-03 | 2024-12-03 | Sunken broken manhole cover in C/way possibly Scottish Water | City of Edinburgh Council | 3711658 | C/way westbound lane under rail bridge Gorgie Road . | City of Edinburgh Council | No | 2024-12-02 10:39
2024-11-08 14:09 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65786 | Accepted | 2024-11-08 | 2024-11-08 | Defective Scottish power cover on fw | City of Edinburgh Council | 3696710 | Gorgie rd 256 at Smithfield st | City of Edinburgh Council | No | 2024-11-07 12:32
2024-10-18 13:34 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65712 | Denied | 2024-10-18 | 2024-10-18 | Damaged footway box | City of Edinburgh Council | 3682859 | Ward 7 ardmillan terrace to stenhouse drive | City of Edinburgh Council | No | 2024-10-17 09:43
2024-08-20 11:16 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65556 | Awaiting Response | 2024-08-20 | 2024-08-20 | Sunken carriageway manhole, Third-Party Reference No. 1815872 | City of Edinburgh Council | 3645489 | Outside ELS House | City of Edinburgh Council | No | 2024-08-19 09:15
2024-08-20 11:12 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65555 | Accepted | 2024-08-20 | 2024-08-20 | Loose footway box | City of Edinburgh Council | 3645474 | Junction Smithfield Street | City of Edinburgh Council | No | 2024-08-19 09:09
2024-06-26 14:10 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65410 | Denied | 2024-06-26 | 2024-06-26 | Unknown cover sunken and noisy | City of Edinburgh Council | 3612647 | Westbound outside of ELS house | City of Edinburgh Council | No | 2024-06-25 12:34
2024-06-03 11:00 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65351 | Accepted | 2024-06-03 | 2024-06-03 | Noisy fire hydrant | City of Edinburgh Council | 3595781 | Carriageway at junction with Coxfield Lane | City of Edinburgh Council | No | 2024-06-02 09:17
2024-05-30 12:03 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65340 | Accepted | 2024-05-30 | 2024-05-30 | Low BT manhole cover causing damage to surrounding area. | City of Edinburgh Council | 3594263 | Just after junction with Hutchison Crossway | City of Edinburgh Council | No | 2024-05-29 14:21
2024-05-13 12:57 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65279 | Awaiting Response | 2024-05-13 | 2024-05-13 | Noisy manhole cover | City of Edinburgh Council | 3581967 | Next to pedestrian crossing,west bound | City of Edinburgh Council | No | 2024-05-13 12:41
2024-05-13 12:19 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65278 | Accepted | 2024-05-13 | 2024-05-13 | Low manhole cover, cracking around cover | City of Edinburgh Council | 3581923 | Opposite 555 Gorgie Road | City of Edinburgh Council | No | 2024-05-13 12:17
2024-05-03 15:55 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65251 | Denied | 2024-05-03 | 2024-05-03 | Noisy carriageway manhole, Third-Party Reference 1740224 | City of Edinburgh Council | 3577052 | Outside ELS House at 555 Gorgie Road | City of Edinburgh Council | No | 2024-05-03 11:42
2024-03-26 14:54 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65102 | Accepted | 2024-03-26 | 2024-03-26 | BT cover loose and noisy (RU: Utility Apparatus) - | City of Edinburgh Council | 3552591 | Gorgie Road - At the junction with Westfield Road (Eastbound) | City of Edinburgh Council | No | 2024-03-24 12:00
2024-03-04 13:47 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65021 | Accepted | 2024-03-04 | 2024-03-04 | Rocking footway manhole cover | City of Edinburgh Council | 3537514 | Outside No 87 | City of Edinburgh Council | No | 2024-03-02 11:44
2024-02-26 14:38 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65006 | Awaiting Response | 2024-02-26 | 2024-02-26 | Sunken carriageway manhole cover | City of Edinburgh Council | 3532573 | Beneath bridge at junction with Robertson Avenue | City of Edinburgh Council | No | 2024-02-23 08:52
2024-01-03 16:49 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64888 | Accepted | 2024-01-03 | 2024-01-03 | Cabinet hit and knocked out of ground | City of Edinburgh Council | 3498003 | Outside Jessie Mays | City of Edinburgh Council | No | 2024-01-03 12:46
2023-11-24 08:56 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64823 | Accepted | 2023-11-24 | 2023-11-24 | Two rocking M/H covers. | City of Edinburgh Council | 3480284 | Gorgie Road adjacent to McLeod Street jct. | City of Edinburgh Council | No | 2023-11-24 08:30
2023-09-27 14:29 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64733 | Accepted | 2023-09-27 | 2023-09-27 | Sunken utility cover, trip hazard. | City of Edinburgh Council | 3445206 | Outside Salvation Army shop. | City of Edinburgh Council | No | 2023-09-27 10:00
2023-09-22 13:15 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64723 | Denied | 2023-09-22 | 2023-09-22 | Damaged manhole cover on carriageway. | City of Edinburgh Council | 3443027 | Outside No 543 | City of Edinburgh Council | No | 2023-09-22 11:14
2023-08-31 15:26 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64685 | Accepted | 2023-08-31 | 2023-08-31 | Gully cover damaged (Enquiry 1605999) | City of Edinburgh Council | 3430414 | Outside McPhersons Fishmongers. | City of Edinburgh Council | No | 2023-08-31 09:06
2023-08-15 14:41 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64654 | Accepted | 2023-08-15 | 2023-08-15 | Covers: Damaged / Defective - Sunken manhole cover (Enquiry 1597071). | City of Edinburgh Council | 3419815 | Outside Els House at Pelican crossing. | City of Edinburgh Council | No | 2023-08-15 11:58
2023-06-28 13:51 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64564 | Accepted | 2023-06-28 | 2023-06-28 | Damaged cover | City of Edinburgh Council | 3391982 | At junction with Tynecastle Lane | City of Edinburgh Council | No | 2023-06-28 10:53
2023-06-13 10:43 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64515 | Denied | 2023-06-13 | 2023-06-13 | Noisy Manhole on carriageway | City of Edinburgh Council | 3381955 | The manhole cover heading east into town is loose and is grey noisy keeping surrounding residents awake at Traffic lights | City of Edinburgh Council | No | 2023-06-12 09:05
2023-01-27 13:49 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64187 | Accepted | 2023-01-27 | 2023-01-27 | Road: Defective / Damaged (Enquiry 1498696) | City of Edinburgh Council | 3293345 | Large man hole cover is sunken into the road and may be loose - is very loud when cars/buses/lorries drive over it. THis is a very busy road and has been disrupting my sleep quite badly. The noise is very loud and echoes across the street. | City of Edinburgh Council | No | 2023-01-27 11:02
2022-12-12 15:02 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64107 | Accepted | 2022-12-12 | 2022-12-12 | Manhole lid raised causing trip hazard at crossing. | City of Edinburgh Council | 3270202 | At Delhaig opposite Riverside House | City of Edinburgh Council | No | 2022-12-09 11:50
2022-12-12 13:38 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64103 | Awaiting Response | 2022-12-12 | 2022-12-12 | Sunken cover on footway | City of Edinburgh Council | 3270092 | At Murieston Road | City of Edinburgh Council | No | 2022-12-09 09:51
2022-12-09 10:45 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64102 | Accepted | 2022-12-09 | 2022-12-09 | Sunken Toby lid | City of Edinburgh Council | 3268964 | Outside 96 | City of Edinburgh Council | No | 2022-12-09 09:46
2022-12-08 11:17 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64099 | Accepted | 2022-12-08 | 2022-12-08 | Concrete in box lid is broken and raised above frame level | City of Edinburgh Council | 3268150 | At bus stop opposite the salvation army | City of Edinburgh Council | No | 2022-12-08 08:50
2022-11-24 12:26 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64063 | Accepted | 2022-11-24 | 2022-11-24 | Road: Defective / Damaged (Enquiry 1466133) | City of Edinburgh Council | 3260004 | Loose manhole cover on road that bangs when driven over. Cracking around the cover o/s 259 Gorgie Rd | City of Edinburgh Council | No | 2022-11-24 08:30
2022-08-23 14:23 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63865 | Denied | 2022-08-23 | 2022-08-23 | 1x Noisy manhole lid | City of Edinburgh Council | 3210880 | Dalry road at the Murieston Crescent junction | City of Edinburgh Council | No | 2022-08-23 13:22
2022-06-21 13:53 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63753 | Accepted | 2022-06-21 | 2022-06-21 | Loose, low noisy Scottish Water manhole cover causing damage to surrounding carriageway | City of Edinburgh Council | 3177938 | Outside Gorgie Road Barber's | City of Edinburgh Council | No | 2022-06-21 12:09
2022-06-07 16:28 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63721 | Accepted | 2022-06-07 | 2022-06-07 | Noisy manhole cover | City of Edinburgh Council | 3169969 | At junction next to Wolseley Trade Counter | City of Edinburgh Council | No | 2022-06-07 10:41
2022-06-07 16:24 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63719 | Accepted | 2022-06-07 | 2022-06-07 | Low Cover | City of Edinburgh Council | 3169962 | At bridge over water west bound just before Pure Gym | City of Edinburgh Council | No | 2022-06-07 11:45
2022-06-07 16:14 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63713 | Denied | 2022-06-07 | 2022-06-07 | Water cover damaged | City of Edinburgh Council | 3169950 | Outside number 20 | City of Edinburgh Council | No | 2022-06-07 12:44
2022-05-02 15:14 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63567 | Accepted | 2022-05-02 | 2022-05-02 | Utility cover sunken | City of Edinburgh Council | 3147961 | Outside number 20 | City of Edinburgh Council | No | 2022-05-02 10:54
2022-04-14 15:47 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63521 | Accepted | 2022-04-14 | 2022-04-14 | Road: Defective / Damaged (Enquiry 1361862) - loose / dropped manhole cover is VERY noisy when vehicles drive over it | City of Edinburgh Council | 3138616 | Outside no 554 | City of Edinburgh Council | No | 2022-04-14 12:59
2022-01-27 14:43 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63049 | Accepted | 2022-01-27 | 2022-01-27 | Low footway manhole cover. | City of Edinburgh Council | 3094859 | Outside Destiny Church | City of Edinburgh Council | No | 2022-01-27 10:10
2021-12-21 12:05 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62906 | Accepted | 2021-12-21 | 2021-12-21 | Rocking noisy carriageway manhole cover and frame. CEC 3rd party ref: 1293180 | City of Edinburgh Council | 3078872 | Opposite No 477 (Laich pub). | City of Edinburgh Council | No | 2021-12-21 06:21
2021-12-16 14:04 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62895 | Accepted | 2021-12-16 | 2021-12-16 | Low noisy carriageway manhole cover. | City of Edinburgh Council | 3077033 | Outside No 546 | City of Edinburgh Council | No | 2021-12-16 11:42
2021-12-14 15:33 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62861 | Accepted | 2021-12-14 | 2021-12-14 | Missing carriageway toby creating pothole. Was temporarily fixed by CEC but has failed again. Blue paint had previously been around the defective apparatus. | City of Edinburgh Council | 3075778 | At junction with Ardmillan Terrace. | City of Edinburgh Council | No | 2021-12-14 14:20
2021-11-24 12:14 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62774 | Accepted | 2021-11-24 | 2021-11-24 | Collapsed carriageway manhole cover and frame. CEC 3rd party ref: 1729474 | City of Edinburgh Council | 3066170 | o/s Springwell House opposite Murieston Lane | City of Edinburgh Council | No | 2021-11-24 07:05
2021-11-24 12:02 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62773 | Accepted | 2021-11-24 | 2021-11-24 | Loose and noisy footway manhole cover. CEC 3rd party ref: 1276974 | City of Edinburgh Council | 3066150 | Just before Chesser Avenue junction eastbound. | City of Edinburgh Council | No | 2021-11-24 08:34
2021-11-16 13:18 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62737 | Accepted | 2021-11-16 | 2021-11-16 | Low cracked noisy manhole. | City of Edinburgh Council | 3061930 | o/s No 266 | City of Edinburgh Council | No | 2021-11-16 07:32
2021-09-28 13:53 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62590 | Accepted | 2021-09-28 | 2021-09-28 | Damaged surround to triple manhole cover. CEC 3rd party ref: 1251863 | City of Edinburgh Council | 3036057 | On footway outside Lift Gyms | City of Edinburgh Council | No | 2021-09-28 08:37
2021-06-17 11:16 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62246 | Accepted | 2021-06-17 | 2021-06-17 | Surround to manhole cover has broken away causing trip hazard. | City of Edinburgh Council | 2985706 | On footway at junction with Westfield Street. | City of Edinburgh Council | No | 2021-06-16 15:20
2021-03-26 08:44 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62048 | Accepted | 2021-03-26 | 2021-03-26 | Moving carriageway manhole cover. | City of Edinburgh Council | 2942055 | o/s The Mill House student accomodation | City of Edinburgh Council | No | 2021-03-24 10:36
2020-12-11 10:37 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A61712 | Accepted | 2020-12-11 | 2020-12-11 | M/hole cover loose and noisy | City of Edinburgh Council | 2890888 | Corner of Saughton Ave and Gorgie Rd | City of Edinburgh Council | No
2020-12-11 10:19 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A61711 | Denied | 2020-12-11 | 2020-12-11 | Noisy C/way Manhole | City of Edinburgh Council | 2890867 | Corner of Saughton Ave and Gorgie Rd | City of Edinburgh Council | No | 2020-12-11 09:03
2020-11-12 11:36 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A61581 | Accepted | 2020-11-12 | 2020-11-12 | Sunken carriageway valve box | City of Edinburgh Council | 2876612 | o/s 572 | City of Edinburgh Council | Yes
2020-11-12 11:13 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A61579 | Accepted | 2020-11-12 | 2020-11-12 | Noisy manhole. | City of Edinburgh Council | 2876541 | Opposite No 470 on c/way | City of Edinburgh Council | Yes
2020-11-12 07:46 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A61577 | Accepted | 2020-11-12 | 2020-11-12 | Noisy manhole | City of Edinburgh Council | 2876263 | Junction Saughton Avenue on c/way | City of Edinburgh Council | Yes
2020-10-30 16:05 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A61555 | Accepted | 2020-10-30 | 2020-10-30 | Loose manhole on C/W | City of Edinburgh Council | 2870247 | O/S 96 | City of Edinburgh Council | Yes
2020-04-07 14:01 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000061219 | Awaiting Response | 2020-04-07 | 2020-04-07 | Noisy manhole. | City of Edinburgh Council | 2784685 | Junction Westfield Road | City of Edinburgh Council | Yes | 2020-04-07 10:07
2020-02-27 11:16 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000061123 | Awaiting Response | 2020-02-27 | 2020-02-27 | Noisy manhole cover. Disturbing nearby residents day and night. CEC 3rd party ref: 967091 | City of Edinburgh Council | 2769153 | o/s 400 (The Mill House) in c/way. | City of Edinburgh Council | Yes | 2020-02-27 10:36
2020-02-25 09:26 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000061116 | Awaiting Response | 2020-02-25 | 2020-02-25 | Noisy manhole. Very loud when vehicles pass over it. CEC 3rd party ref: 965216 | City of Edinburgh Council | 2767573 | At McDonalds on c/way. | City of Edinburgh Council | Yes | 2020-02-24 14:26
2020-01-06 10:46 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000060903 | Abandoned | 2020-01-06 | 2020-01-06 | Noisy manhole. | City of Edinburgh Council | 2741558 | At side of 1 Saughton Avenue on c/way. | City of Edinburgh Council | Yes | 2020-11-11 11:22
2019-10-03 15:03 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000060587 | Abandoned | 2019-10-03 | 2019-10-03 | Missing toby cover. CEC 3rd party ref: 895859 | City of Edinburgh Council | 2702701 | Close to 116 on footway | City of Edinburgh Council | Yes | 2019-10-03 11:29
2019-08-01 17:14 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000060067 | Abandoned | 2019-08-01 | 2019-08-01 | Burst pipe in footway | City of Edinburgh Council | 2673022 | at 227 | City of Edinburgh Council | Yes | 2019-07-31 11:58
2019-02-11 17:42 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000058459 | Abandoned | 2019-02-11 | 2019-02-11 | Covers: Missing - Cover is missing (Enquiry 796102) | City of Edinburgh Council | 2585430 | Outside no 502 Gorgie Road ( Riverside House ) at crossing point in f / way. | City of Edinburgh Council | Yes | 2019-02-11 09:18
2018-11-12 14:17 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000057745 | Abandoned | 2018-11-12 | 2018-11-12 | Half of manhole cover on footway is missing. CEC 3rd party ref: 744381 | City of Edinburgh Council | 2547338 | o/s 496 | City of Edinburgh Council | Yes | 2018-11-12 08:47
2018-08-29 16:43 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000056852 | Abandoned | 2018-08-29 | 2018-08-29 | Collapsed m / hole cover in f / way | City of Edinburgh Council | 2512063 | Opposite no 598/no | City of Edinburgh Council | Yes | 2018-08-29 13:18
2017-08-01 14:49 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000052777 | Abandoned | 2017-08-01 | 2017-08-01 | Cavity next to Scottish Power box surrounds on footway at kerb. Cable exposed. Scottish Power logged call ref: 121975F. CEC 3rd party ref: 531260 | City of Edinburgh Council | 2319460 | On junction with Chesser Avenue. | City of Edinburgh Council | Yes | 2017-08-01 11:35
2017-07-27 11:06 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000052753 | Abandoned | 2017-07-27 | 2017-07-27 | Low m / hole in f / way | City of Edinburgh Council | 2317292 | o/s No250. | City of Edinburgh Council | Yes | 2017-07-27 09:37
2017-04-28 11:22 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000051585 | Abandoned | 2017-04-28 | 2017-04-28 | Damaged triple manhole cover | City of Edinburgh Council | 2270247 | Westbound o/s Plumb Center Showroom. Near LP 45 approx 200m prior to Alexander Drive | City of Edinburgh Council | Yes | 2017-04-28 10:09
2017-04-21 11:46 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000051514 | Abandoned | 2017-04-21 | 2017-04-21 | Rocking manhole cover. | City of Edinburgh Council | 2266201 | Opp 443 on eastbound carriageway. | City of Edinburgh Council | Yes | 2017-04-21 11:25
2017-02-01 11:52 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000050798 | Abandoned | 2017-02-01 | 2017-02-01 | Sunken toby cover. | City of Edinburgh Council | 2220329 | o/s 223 in footway. | City of Edinburgh Council | Yes
2015-01-26 15:16 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000041735 | Abandoned | 2015-01-26 | 2015-01-26 | Low and rocking manhole. | City of Edinburgh Council | 1854075 | Approx 70m west of Chesser Ave just prior to bus stop on w/bound c/way. | City of Edinburgh Council | Yes
2012-08-29 18:46 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000029517 | Abandoned | 2012-08-29 | 2012-08-29 | Double Fibreway cover requires replacement to be provided to Tarmac by 10/09/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract) | City of Edinburgh Council | 1423434 | centre of c/way at jct of Tynecastle Terrace | City of Edinburgh Council | Yes
2011-12-21 11:18 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025336 | Abandoned | 2011-12-21 | 2011-12-21 | Manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1293153 | Westbound carriageway west of Murieston Lane. | City of Edinburgh Council | Yes
2011-12-21 11:07 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025334 | Abandoned | 2011-12-21 | 2011-12-21 | Manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1293128 | Eastbound carriageway west of Murieston Lane. | City of Edinburgh Council | Yes
2011-12-21 10:58 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025331 | Abandoned | 2011-12-21 | 2011-12-21 | Triple manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1293110 | Eastbound carriageway at junction of McLeod Street. | City of Edinburgh Council | Yes
2011-12-21 10:47 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025330 | Abandoned | 2011-12-21 | 2011-12-21 | Triple manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1293098 | Eastbound carriageway west of Newton Street. | City of Edinburgh Council | Yes
2011-12-21 10:37 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025328 | Abandoned | 2011-12-21 | 2011-12-21 | Double manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1293079 | Westbound carriageway east of Tynecastle Terrace. | City of Edinburgh Council | Yes
2011-12-20 11:14 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025311 | Abandoned | 2011-12-20 | 2011-12-20 | Double manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1292582 | Centre of carriageway at junction of Tynecastle Terrace. | City of Edinburgh Council | Yes
2011-12-20 11:01 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025310 | Abandoned | 2011-12-20 | 2011-12-20 | Double manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1292549 | Centre of carriageway at junction of Tynecastle Terrace. | City of Edinburgh Council | Yes
2011-12-20 10:50 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025309 | Abandoned | 2011-12-20 | 2011-12-20 | Manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1292526 | Eastbound carriageway at junction of Wheatfield Street. | City of Edinburgh Council | Yes
2011-12-20 10:35 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025307 | Abandoned | 2011-12-20 | 2011-12-20 | Triple cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1292503 | Eastbound carriageway at junction of Wheatfield Street. | City of Edinburgh Council | Yes

## Location at Robertson Avenue
Phase Created | Road | Address 2 | Category | Activity Reference | Status | Start Date | End Date | Description | Auth | Local Ref | Location | Prom Organisation | Contractor | Originator | Activity Att? | Latest Inspection Date
2025-05-08 07:32 | Gorgie Road | Gorgie, Edinburgh | Accepted Works | SG023-GORGIE-ROAD-TOBY | Accepted | 2025-05-08 | 2025-05-08 | Sunken cover on carriageway | City of Edinburgh Council | 3810532 | At junction with Robertson Avenue under rail bridge | SGN |  |  | No | 2025-04-15 14:09
2025-04-28 09:48 | Gorgie Road | Gorgie, Edinburgh | Minor With Excavation | VF042-BRM4061-DEF0833 | Closed | 2025-05-29 | 2025-05-30 | DEFECT - Two double manhole covers (Norwood Telecom) low and noisy on carriageway. | City of Edinburgh Council | 3797025 | At junction with Robertson Avenue under rail bridge | Vodafone Limited | BRM Utility Services |  | No | 2025-04-15 14:03
2025-04-16 09:43 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66343 | Accepted | 2025-04-16 | 2025-04-16 | Two double manhole covers (Norwood Telecom) low and noisy on carriageway. | City of Edinburgh Council | 3796916 | At junction with Robertson Avenue under rail bridge | City of Edinburgh Council |  |  | No | 2025-04-15 14:03
2025-04-16 09:24 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66342 | Accepted | 2025-04-16 | 2025-04-16 | Sunken cover on carriageway | City of Edinburgh Council | 3796884 | At junction with Robertson Avenue under rail bridge | City of Edinburgh Council |  |  | No | 2025-04-15 14:09
2025-02-19 09:17 | Gorgie Road | Gorgie, Edinburgh | Minor With Excavation | SP400-2100003212B | Closed | 2025-04-07 | 2025-04-09 | **PERM PHASE** - Make interim perm | City of Edinburgh Council | 2464148 | From jct Robertson Avenue to jct Westfield Rd | SP Energy Networks | Morrison Utility Services |  | Yes | 2025-04-09 07:30
2024-07-09 15:55 | Gorgie Road | Gorgie, Edinburgh | Minor Without Excavation | CE010-S149 | Closed No Excavation | 2024-07-10 | 2024-07-11 | Urgent Works - Pest Control | City of Edinburgh Council | 3620635 | At junction with Wheatfield Road and Robertson Avenue including extents of railway bridge | City of Edinburgh Council |  |  | No
2024-02-26 14:38 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65006 | Awaiting Response | 2024-02-26 | 2024-02-26 | Sunken carriageway manhole cover | City of Edinburgh Council | 3532573 | Beneath bridge at junction with Robertson Avenue | City of Edinburgh Council |  |  | No | 2024-02-23 08:52
2020-02-21 10:55 | Gorgie Road | Gorgie, Edinburgh | Major | SG023-SCN2102/1 | Closed | 2021-01-11 | 2021-01-20 | ABANDON AND REPLACE EXISTING CI MAIN WITH PE MAIN | City of Edinburgh Council | 2766165 | @ JUNC ROBERTSON AVE | SGN |  |  | No
2017-11-06 15:33 | Gorgie Road | Gorgie, Edinburgh | Standard | SP010-SPT1243969-45/GORG | Closed | 2018-01-09 | 2018-01-15 | Excavations to locate blockages | City of Edinburgh Council | 2366280 | At junction with Robertson Avenue - Opp No 410 - o/s No 435 - Plotted on sites tab | SP Energy Networks | C-Plan Telecommunications |  | Yes | 2019-11-29 12:35
2017-10-02 15:38 | Gorgie Road | Gorgie, Edinburgh | Minor Without Excavation | SP010-SP1243969/56 | Closed No Excavation | 2017-10-05 | 2017-10-05 | Test road and rope | City of Edinburgh Council | 2349586 | At junction with Robertson Avenue - Opp No 410 - o/s No 435 - Plotted on sites tab | SP Energy Networks | C-Plan Telecommunications |  | No
2017-09-12 12:02 | Gorgie Road | Gorgie, Edinburgh | Minor Without Excavation | SP010-SPT1243969-45/GORGI | Closed No Excavation | 2017-09-18 | 2017-09-20 | *** ROAD OCCUPATION ONLY *** Cabling works within pre installed ducts and pre built boxes | City of Edinburgh Council | 2339831 | At junction with Robertson Avenue - Opp No 410 - o/s No 435 - Plotted on sites tab | SP Energy Networks | C-Plan Telecommunications |  | No
2016-04-14 15:30 | Gorgie Road | Gorgie, Edinburgh | Minor With Excavation | CF001-CFH-EDNB-017 | Closed | 2016-06-19 | 2016-06-19 | Remedial works to be completed. | City of Edinburgh Council | 2075522 | At the junction with Robertson Avenue | CityFibre Metro Networks Ltd | KN Group | Cityfibre | Yes | 2018-04-16 11:19
2016-04-14 09:59 | Gorgie Road | Gorgie, Edinburgh | Remedial Other | SW100-04739828/MGI | Closed | 2016-05-15 | 2016-05-15 | Defective manhole. | City of Edinburgh Council | 1821555 | Rail bridge west of Wheatfield Road and Robertson Avenue. | Scottish Water |  |  | Yes | 2018-04-11 11:54
2012-10-18 10:01 | Gorgie Road | Gorgie, Edinburgh | Urgent | SP003-SLE9100574855 | Closed | 2012-10-13 | 2012-10-19 | *** RETROSPECTIVE NOTICE *** SL Fault | City of Edinburgh Council | 1447922 | At junction with Robertson Avenue | SP Energy Networks | Clancy Docwra [New Contract] |  | Yes | 2014-09-16 14:25

## Defective Apparatus Ironworks
Phase Created | Road | Address 2 | Category | Activity Reference | Status | Start Date | End Date | Description | Auth | Local Ref | Location | Prom Organisation | Contractor | Originator | Activity Att? | Latest Inspection Date
2025-08-07 14:35 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66710 | Awaiting Response | 2025-08-07 | 2025-08-07 | 2x double sky manhole covers sunken loose and noisy | City of Edinburgh Council | 3872109 | On Gorgie Road at junction with Mcleod Street. | City of Edinburgh Council |  |  | No | 2025-08-07 10:57
2025-08-06 18:32 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66707 | Denied | 2025-08-06 | 2025-08-06 | BT phone box has been damaged | City of Edinburgh Council | 3871385 | Outside the polish shop 364 Gorgie Road on footway | City of Edinburgh Council |  |  | No | 2025-08-06 14:52
2025-06-27 14:02 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66575 | Accepted | 2025-06-27 | 2025-06-27 | Double BT manhole loose and noisy on carriageway | City of Edinburgh Council | 3845714 | Coming off Balgreen Road left to Gorgie Road | City of Edinburgh Council |  |  | No | 2025-06-27 11:45
2025-06-27 13:45 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66574 | Accepted | 2025-06-27 | 2025-06-27 | Sunken and noisy BT manhole in c/way | City of Edinburgh Council | 3845693 | Outside Gorgie laundrette | City of Edinburgh Council |  |  | No | 2025-06-27 12:31
2025-06-13 17:16 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66526 | Denied | 2025-06-13 | 2025-06-13 | Manhole on footway collapsed. Made safe with cones | City of Edinburgh Council | 3836706 | Outside The Salvation Army, No's 254 to No. 256 | City of Edinburgh Council |  |  | No | 2025-06-13 10:00
2025-05-28 12:15 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66477 | Accepted | 2025-05-28 | 2025-05-28 | Vodafone double concrete manhole broken | City of Edinburgh Council | 3824591 | Outside 351 on footway | City of Edinburgh Council |  |  | No | 2025-05-28 09:17
2025-05-21 14:41 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66459 | Denied | 2025-05-21 | 2025-05-21 | Scottish Water Toby's raised above footway | City of Edinburgh Council | 3820281 | Outside 12 on footway | City of Edinburgh Council |  |  | No | 2025-05-21 10:31
2025-05-21 14:03 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66457 | Denied | 2025-05-21 | 2025-05-21 | Manhole sinking making footway uneven | City of Edinburgh Council | 3820205 | Outside 18 on footway | City of Edinburgh Council |  |  | No | 2025-05-21 10:29
2025-05-02 15:13 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66410 | Accepted | 2025-05-02 | 2025-05-02 | Loose and noisy BT cover on carriageway | City of Edinburgh Council | 3807958 | Outside 398 Gorgie Road, Spice of Asia | City of Edinburgh Council |  |  | No | 2025-05-01 11:08
2025-05-02 12:49 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66406 | Accepted | 2025-05-02 | 2025-05-02 | Manhole cover loose and noisy | City of Edinburgh Council | 3807752 | At traffic lights at the junction to Balgreen Road | City of Edinburgh Council |  |  | No | 2025-05-01 11:16
2025-04-16 09:43 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66343 | Accepted | 2025-04-16 | 2025-04-16 | Two double manhole covers (Norwood Telecom) low and noisy on carriageway. | City of Edinburgh Council | 3796916 | At junction with Robertson Avenue under rail bridge | City of Edinburgh Council |  |  | No | 2025-04-15 14:03
2025-04-16 09:24 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66342 | Accepted | 2025-04-16 | 2025-04-16 | Sunken cover on carriageway | City of Edinburgh Council | 3796884 | At junction with Robertson Avenue under rail bridge | City of Edinburgh Council |  |  | No | 2025-04-15 14:09
2025-03-17 16:01 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66210 | Accepted | 2025-03-17 | 2025-03-17 | Rocking and noisy manhole at pedestrian crossing in carriageway | City of Edinburgh Council | 3775766 | At Traffic lights at VPZ shop 193 Gorgie Road near to Wardlaw Place | City of Edinburgh Council |  |  | No | 2025-03-17 12:27
2025-02-18 14:34 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66094 | Denied | 2025-02-18 | 2025-02-18 | Damage to drainage Clay pipe causing subsidence on footway at manhole, made safe with walkboard. | City of Edinburgh Council | 3756514 | Outside Stratfords Bar from 227-229 Gorgie Road | City of Edinburgh Council |  |  | No | 2025-02-18 14:09
2025-02-07 13:17 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A66066 | Accepted | 2025-02-07 | 2025-02-07 | Loose and noisy bt manhole on city bound carriageway | City of Edinburgh Council | 3749429 | Outside 352 Gorgie road | City of Edinburgh Council |  |  | No | 2025-02-06 10:26
2025-01-14 15:34 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65965 | Accepted | 2025-01-14 | 2025-01-14 | Sunken cover on footway at ductiles see pictures | City of Edinburgh Council | 3732436 | On the footway crossing at Murieston Road/dalry junction | City of Edinburgh Council |  |  | No | 2025-01-14 10:30
2025-01-09 16:04 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65950 | Denied | 2025-01-09 | 2025-01-09 | Scottish water sunken slabbed area around manhole | City of Edinburgh Council | 3729428 | Outside Stratford bar | City of Edinburgh Council |  |  | No | 2025-01-09 14:00
2024-12-20 13:33 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65899 | Denied | 2024-12-20 | 2024-12-20 | Sunken cover, damaged surround | City of Edinburgh Council | 3722886 | Between 387 and 389 | City of Edinburgh Council |  |  | No | 2024-12-18 13:22
2024-12-19 16:41 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65895 | Denied | 2024-12-19 | 2024-12-19 | Sunken cover, damaged surround | City of Edinburgh Council | 3722354 | Between 387 and 389 | City of Edinburgh Council |  |  | No | 2024-12-18 01:32
2024-12-19 16:02 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65892 | Accepted | 2024-12-19 | 2024-12-19 | Sunken cover, damaged surround | City of Edinburgh Council | 3722318 | Adjacent to 466 gorgie road | City of Edinburgh Council |  |  | No | 2024-12-18 13:20
2024-12-03 11:29 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65848 | Accepted | 2024-12-03 | 2024-12-03 | Sunken broken manhole cover in C/way possibly Scottish Water | City of Edinburgh Council | 3711658 | C/way westbound lane under rail bridge Gorgie Road . | City of Edinburgh Council |  |  | No | 2024-12-02 10:39
2024-11-08 14:09 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65786 | Accepted | 2024-11-08 | 2024-11-08 | Defective Scottish power cover on fw | City of Edinburgh Council | 3696710 | Gorgie rd 256 at Smithfield st | City of Edinburgh Council |  |  | No | 2024-11-07 12:32
2024-10-18 13:34 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65712 | Denied | 2024-10-18 | 2024-10-18 | Damaged footway box | City of Edinburgh Council | 3682859 | Ward 7 ardmillan terrace to stenhouse drive | City of Edinburgh Council |  |  | No | 2024-10-17 09:43
2024-08-20 11:16 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65556 | Awaiting Response | 2024-08-20 | 2024-08-20 | Sunken carriageway manhole, Third-Party Reference No. 1815872 | City of Edinburgh Council | 3645489 | Outside ELS House | City of Edinburgh Council |  |  | No | 2024-08-19 09:15
2024-08-20 11:12 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65555 | Accepted | 2024-08-20 | 2024-08-20 | Loose footway box | City of Edinburgh Council | 3645474 | Junction Smithfield Street | City of Edinburgh Council |  |  | No | 2024-08-19 09:09
2024-06-26 14:10 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65410 | Denied | 2024-06-26 | 2024-06-26 | Unknown cover sunken and noisy | City of Edinburgh Council | 3612647 | Westbound outside of ELS house | City of Edinburgh Council |  |  | No | 2024-06-25 12:34
2024-06-03 11:00 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65351 | Accepted | 2024-06-03 | 2024-06-03 | Noisy fire hydrant | City of Edinburgh Council | 3595781 | Carriageway at junction with Coxfield Lane | City of Edinburgh Council |  |  | No | 2024-06-02 09:17
2024-05-30 12:03 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65340 | Accepted | 2024-05-30 | 2024-05-30 | Low BT manhole cover causing damage to surrounding area. | City of Edinburgh Council | 3594263 | Just after junction with Hutchison Crossway | City of Edinburgh Council |  |  | No | 2024-05-29 14:21
2024-05-13 12:57 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65279 | Awaiting Response | 2024-05-13 | 2024-05-13 | Noisy manhole cover | City of Edinburgh Council | 3581967 | Next to pedestrian crossing,west bound | City of Edinburgh Council |  |  | No | 2024-05-13 12:41
2024-05-13 12:19 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65278 | Accepted | 2024-05-13 | 2024-05-13 | Low manhole cover, cracking around cover | City of Edinburgh Council | 3581923 | Opposite 555 Gorgie Road | City of Edinburgh Council |  |  | No | 2024-05-13 12:17
2024-05-03 15:55 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65251 | Denied | 2024-05-03 | 2024-05-03 | Noisy carriageway manhole, Third-Party Reference 1740224 | City of Edinburgh Council | 3577052 | Outside ELS House at 555 Gorgie Road | City of Edinburgh Council |  |  | No | 2024-05-03 11:42
2024-03-26 14:54 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65102 | Accepted | 2024-03-26 | 2024-03-26 | BT cover loose and noisy (RU: Utility Apparatus) - | City of Edinburgh Council | 3552591 | Gorgie Road - At the junction with Westfield Road (Eastbound) | City of Edinburgh Council |  |  | No | 2024-03-24 12:00
2024-03-04 13:47 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65021 | Accepted | 2024-03-04 | 2024-03-04 | Rocking footway manhole cover | City of Edinburgh Council | 3537514 | Outside No 87 | City of Edinburgh Council |  |  | No | 2024-03-02 11:44
2024-02-26 14:38 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A65006 | Awaiting Response | 2024-02-26 | 2024-02-26 | Sunken carriageway manhole cover | City of Edinburgh Council | 3532573 | Beneath bridge at junction with Robertson Avenue | City of Edinburgh Council |  |  | No | 2024-02-23 08:52
2024-01-03 16:49 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64888 | Accepted | 2024-01-03 | 2024-01-03 | Cabinet hit and knocked out of ground | City of Edinburgh Council | 3498003 | Outside Jessie Mays | City of Edinburgh Council |  |  | No | 2024-01-03 12:46
2023-11-24 08:56 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64823 | Accepted | 2023-11-24 | 2023-11-24 | Two rocking M/H covers. | City of Edinburgh Council | 3480284 | Gorgie Road adjacent to McLeod Street jct. | City of Edinburgh Council |  |  | No | 2023-11-24 08:30
2023-09-27 14:29 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64733 | Accepted | 2023-09-27 | 2023-09-27 | Sunken utility cover, trip hazard. | City of Edinburgh Council | 3445206 | Outside Salvation Army shop. | City of Edinburgh Council |  |  | No | 2023-09-27 10:00
2023-09-22 13:15 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64723 | Denied | 2023-09-22 | 2023-09-22 | Damaged manhole cover on carriageway. | City of Edinburgh Council | 3443027 | Outside No 543 | City of Edinburgh Council |  |  | No | 2023-09-22 11:14
2023-08-31 15:26 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64685 | Accepted | 2023-08-31 | 2023-08-31 | Gully cover damaged (Enquiry 1605999) | City of Edinburgh Council | 3430414 | Outside McPhersons Fishmongers. | City of Edinburgh Council |  |  | No | 2023-08-31 09:06
2023-08-15 14:41 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64654 | Accepted | 2023-08-15 | 2023-08-15 | Covers: Damaged / Defective - Sunken manhole cover (Enquiry 1597071). | City of Edinburgh Council | 3419815 | Outside Els House at Pelican crossing. | City of Edinburgh Council |  |  | No | 2023-08-15 11:58
2023-06-28 13:51 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64564 | Accepted | 2023-06-28 | 2023-06-28 | Damaged cover | City of Edinburgh Council | 3391982 | At junction with Tynecastle Lane | City of Edinburgh Council |  |  | No | 2023-06-28 10:53
2023-06-13 10:43 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64515 | Denied | 2023-06-13 | 2023-06-13 | Noisy Manhole on carriageway | City of Edinburgh Council | 3381955 | The manhole cover heading east into town is loose and is grey noisy keeping surrounding residents awake at Traffic lights | City of Edinburgh Council |  |  | No | 2023-06-12 09:05
2023-01-27 13:49 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64187 | Accepted | 2023-01-27 | 2023-01-27 | Road: Defective / Damaged (Enquiry 1498696) | City of Edinburgh Council | 3293345 | Large man hole cover is sunken into the road and may be loose - is very loud when cars/buses/lorries drive over it. THis is a very busy road and has been disrupting my sleep quite badly. The noise is very loud and echoes across the street. | City of Edinburgh Council |  |  | No | 2023-01-27 11:02
2022-12-12 15:02 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64107 | Accepted | 2022-12-12 | 2022-12-12 | Manhole lid raised causing trip hazard at crossing. | City of Edinburgh Council | 3270202 | At Delhaig opposite Riverside House | City of Edinburgh Council |  |  | No | 2022-12-09 11:50
2022-12-12 13:38 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64103 | Awaiting Response | 2022-12-12 | 2022-12-12 | Sunken cover on footway | City of Edinburgh Council | 3270092 | At Murieston Road | City of Edinburgh Council |  |  | No | 2022-12-09 09:51
2022-12-09 10:45 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64102 | Accepted | 2022-12-09 | 2022-12-09 | Sunken Toby lid | City of Edinburgh Council | 3268964 | Outside 96 | City of Edinburgh Council |  |  | No | 2022-12-09 09:46
2022-12-08 11:17 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64099 | Accepted | 2022-12-08 | 2022-12-08 | Concrete in box lid is broken and raised above frame level | City of Edinburgh Council | 3268150 | At bus stop opposite the salvation army | City of Edinburgh Council |  |  | No | 2022-12-08 08:50
2022-11-24 12:26 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A64063 | Accepted | 2022-11-24 | 2022-11-24 | Road: Defective / Damaged (Enquiry 1466133) | City of Edinburgh Council | 3260004 | Loose manhole cover on road that bangs when driven over. Cracking around the cover o/s 259 Gorgie Rd | City of Edinburgh Council |  |  | No | 2022-11-24 08:30
2022-08-23 14:23 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63865 | Denied | 2022-08-23 | 2022-08-23 | 1x Noisy manhole lid | City of Edinburgh Council | 3210880 | Dalry road at the Murieston Crescent junction | City of Edinburgh Council |  |  | No | 2022-08-23 13:22
2022-06-21 13:53 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63753 | Accepted | 2022-06-21 | 2022-06-21 | Loose, low noisy Scottish Water manhole cover causing damage to surrounding carriageway | City of Edinburgh Council | 3177938 | Outside Gorgie Road Barber's | City of Edinburgh Council |  |  | No | 2022-06-21 12:09
2022-06-07 16:28 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63721 | Accepted | 2022-06-07 | 2022-06-07 | Noisy manhole cover | City of Edinburgh Council | 3169969 | At junction next to Wolseley Trade Counter | City of Edinburgh Council |  |  | No | 2022-06-07 10:41
2022-06-07 16:24 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63719 | Accepted | 2022-06-07 | 2022-06-07 | Low Cover | City of Edinburgh Council | 3169962 | At bridge over water west bound just before Pure Gym | City of Edinburgh Council |  |  | No | 2022-06-07 11:45
2022-06-07 16:14 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63713 | Denied | 2022-06-07 | 2022-06-07 | Water cover damaged | City of Edinburgh Council | 3169950 | Outside number 20 | City of Edinburgh Council |  |  | No | 2022-06-07 12:44
2022-05-02 15:14 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63567 | Accepted | 2022-05-02 | 2022-05-02 | Utility cover sunken | City of Edinburgh Council | 3147961 | Outside number 20 | City of Edinburgh Council |  |  | No | 2022-05-02 10:54
2022-04-14 15:47 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63521 | Accepted | 2022-04-14 | 2022-04-14 | Road: Defective / Damaged (Enquiry 1361862) - loose / dropped manhole cover is VERY noisy when vehicles drive over it | City of Edinburgh Council | 3138616 | Outside no 554 | City of Edinburgh Council |  |  | No | 2022-04-14 12:59
2022-01-27 14:43 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A63049 | Accepted | 2022-01-27 | 2022-01-27 | Low footway manhole cover. | City of Edinburgh Council | 3094859 | Outside Destiny Church | City of Edinburgh Council |  |  | No | 2022-01-27 10:10
2021-12-21 12:05 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62906 | Accepted | 2021-12-21 | 2021-12-21 | Rocking noisy carriageway manhole cover and frame. CEC 3rd party ref: 1293180 | City of Edinburgh Council | 3078872 | Opposite No 477 (Laich pub). | City of Edinburgh Council |  |  | No | 2021-12-21 06:21
2021-12-16 14:04 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62895 | Accepted | 2021-12-16 | 2021-12-16 | Low noisy carriageway manhole cover. | City of Edinburgh Council | 3077033 | Outside No 546 | City of Edinburgh Council |  |  | No | 2021-12-16 11:42
2021-12-14 15:33 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62861 | Accepted | 2021-12-14 | 2021-12-14 | Missing carriageway toby creating pothole. Was temporarily fixed by CEC but has failed again. Blue paint had previously been around the defective apparatus. | City of Edinburgh Council | 3075778 | At junction with Ardmillan Terrace. | City of Edinburgh Council |  |  | No | 2021-12-14 14:20
2021-11-24 12:14 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62774 | Accepted | 2021-11-24 | 2021-11-24 | Collapsed carriageway manhole cover and frame. CEC 3rd party ref: 1729474 | City of Edinburgh Council | 3066170 | o/s Springwell House opposite Murieston Lane | City of Edinburgh Council |  |  | No | 2021-11-24 07:05
2021-11-24 12:02 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62773 | Accepted | 2021-11-24 | 2021-11-24 | Loose and noisy footway manhole cover. CEC 3rd party ref: 1276974 | City of Edinburgh Council | 3066150 | Just before Chesser Avenue junction eastbound. | City of Edinburgh Council |  |  | No | 2021-11-24 08:34
2021-11-16 13:18 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62737 | Accepted | 2021-11-16 | 2021-11-16 | Low cracked noisy manhole. | City of Edinburgh Council | 3061930 | o/s No 266 | City of Edinburgh Council |  |  | No | 2021-11-16 07:32
2021-09-28 13:53 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62590 | Accepted | 2021-09-28 | 2021-09-28 | Damaged surround to triple manhole cover. CEC 3rd party ref: 1251863 | City of Edinburgh Council | 3036057 | On footway outside Lift Gyms | City of Edinburgh Council |  |  | No | 2021-09-28 08:37
2021-06-17 11:16 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62246 | Accepted | 2021-06-17 | 2021-06-17 | Surround to manhole cover has broken away causing trip hazard. | City of Edinburgh Council | 2985706 | On footway at junction with Westfield Street. | City of Edinburgh Council |  |  | No | 2021-06-16 15:20
2021-03-26 08:44 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A62048 | Accepted | 2021-03-26 | 2021-03-26 | Moving carriageway manhole cover. | City of Edinburgh Council | 2942055 | o/s The Mill House student accomodation | City of Edinburgh Council |  |  | No | 2021-03-24 10:36
2020-12-11 10:37 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A61712 | Accepted | 2020-12-11 | 2020-12-11 | M/hole cover loose and noisy | City of Edinburgh Council | 2890888 | Corner of Saughton Ave and Gorgie Rd | City of Edinburgh Council |  |  | No
2020-12-11 10:19 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A61711 | Denied | 2020-12-11 | 2020-12-11 | Noisy C/way Manhole | City of Edinburgh Council | 2890867 | Corner of Saughton Ave and Gorgie Rd | City of Edinburgh Council |  |  | No | 2020-12-11 09:03
2020-11-12 11:36 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A61581 | Accepted | 2020-11-12 | 2020-11-12 | Sunken carriageway valve box | City of Edinburgh Council | 2876612 | o/s 572 | City of Edinburgh Council |  |  | Yes
2020-11-12 11:13 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A61579 | Accepted | 2020-11-12 | 2020-11-12 | Noisy manhole. | City of Edinburgh Council | 2876541 | Opposite No 470 on c/way | City of Edinburgh Council |  |  | Yes
2020-11-12 07:46 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A61577 | Accepted | 2020-11-12 | 2020-11-12 | Noisy manhole | City of Edinburgh Council | 2876263 | Junction Saughton Avenue on c/way | City of Edinburgh Council |  |  | Yes
2020-10-30 16:05 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A61555 | Accepted | 2020-10-30 | 2020-10-30 | Loose manhole on C/W | City of Edinburgh Council | 2870247 | O/S 96 | City of Edinburgh Council |  |  | Yes
2020-04-07 14:01 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000061219 | Awaiting Response | 2020-04-07 | 2020-04-07 | Noisy manhole. | City of Edinburgh Council | 2784685 | Junction Westfield Road | City of Edinburgh Council |  |  | Yes | 2020-04-07 10:07
2020-02-27 11:16 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000061123 | Awaiting Response | 2020-02-27 | 2020-02-27 | Noisy manhole cover. Disturbing nearby residents day and night. CEC 3rd party ref: 967091 | City of Edinburgh Council | 2769153 | o/s 400 (The Mill House) in c/way. | City of Edinburgh Council |  |  | Yes | 2020-02-27 10:36
2020-02-25 09:26 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000061116 | Awaiting Response | 2020-02-25 | 2020-02-25 | Noisy manhole. Very loud when vehicles pass over it. CEC 3rd party ref: 965216 | City of Edinburgh Council | 2767573 | At McDonalds on c/way. | City of Edinburgh Council |  |  | Yes | 2020-02-24 14:26
2020-01-06 10:46 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000060903 | Abandoned | 2020-01-06 | 2020-01-06 | Noisy manhole. | City of Edinburgh Council | 2741558 | At side of 1 Saughton Avenue on c/way. | City of Edinburgh Council |  |  | Yes | 2020-11-11 11:22
2019-10-03 15:03 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000060587 | Abandoned | 2019-10-03 | 2019-10-03 | Missing toby cover. CEC 3rd party ref: 895859 | City of Edinburgh Council | 2702701 | Close to 116 on footway | City of Edinburgh Council |  |  | Yes | 2019-10-03 11:29
2019-08-01 17:14 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000060067 | Abandoned | 2019-08-01 | 2019-08-01 | Burst pipe in footway | City of Edinburgh Council | 2673022 | at 227 | City of Edinburgh Council |  |  | Yes | 2019-07-31 11:58
2019-02-11 17:42 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000058459 | Abandoned | 2019-02-11 | 2019-02-11 | Covers: Missing - Cover is missing (Enquiry 796102) | City of Edinburgh Council | 2585430 | Outside no 502 Gorgie Road ( Riverside House ) at crossing point in f / way. | City of Edinburgh Council |  |  | Yes | 2019-02-11 09:18
2018-11-12 14:17 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000057745 | Abandoned | 2018-11-12 | 2018-11-12 | Half of manhole cover on footway is missing. CEC 3rd party ref: 744381 | City of Edinburgh Council | 2547338 | o/s 496 | City of Edinburgh Council |  |  | Yes | 2018-11-12 08:47
2018-08-29 16:43 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000056852 | Abandoned | 2018-08-29 | 2018-08-29 | Collapsed m / hole cover in f / way | City of Edinburgh Council | 2512063 | Opposite no 598/no | City of Edinburgh Council |  |  | Yes | 2018-08-29 13:18
2017-08-01 14:49 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000052777 | Abandoned | 2017-08-01 | 2017-08-01 | Cavity next to Scottish Power box surrounds on footway at kerb. Cable exposed. Scottish Power logged call ref: 121975F. CEC 3rd party ref: 531260 | City of Edinburgh Council | 2319460 | On junction with Chesser Avenue. | City of Edinburgh Council |  |  | Yes | 2017-08-01 11:35
2017-07-27 11:06 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000052753 | Abandoned | 2017-07-27 | 2017-07-27 | Low m / hole in f / way | City of Edinburgh Council | 2317292 | o/s No250. | City of Edinburgh Council |  |  | Yes | 2017-07-27 09:37
2017-04-28 11:22 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000051585 | Abandoned | 2017-04-28 | 2017-04-28 | Damaged triple manhole cover | City of Edinburgh Council | 2270247 | Westbound o/s Plumb Center Showroom. Near LP 45 approx 200m prior to Alexander Drive | City of Edinburgh Council |  |  | Yes | 2017-04-28 10:09
2017-04-21 11:46 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000051514 | Abandoned | 2017-04-21 | 2017-04-21 | Rocking manhole cover. | City of Edinburgh Council | 2266201 | Opp 443 on eastbound carriageway. | City of Edinburgh Council |  |  | Yes | 2017-04-21 11:25
2017-02-01 11:52 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000050798 | Abandoned | 2017-02-01 | 2017-02-01 | Sunken toby cover. | City of Edinburgh Council | 2220329 | o/s 223 in footway. | City of Edinburgh Council |  |  | Yes
2015-01-26 15:16 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000041735 | Abandoned | 2015-01-26 | 2015-01-26 | Low and rocking manhole. | City of Edinburgh Council | 1854075 | Approx 70m west of Chesser Ave just prior to bus stop on w/bound c/way. | City of Edinburgh Council |  |  | Yes
2012-08-29 18:46 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000029517 | Abandoned | 2012-08-29 | 2012-08-29 | Double Fibreway cover requires replacement to be provided to Tarmac by 10/09/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract) | City of Edinburgh Council | 1423434 | centre of c/way at jct of Tynecastle Terrace | City of Edinburgh Council |  |  | Yes
2011-12-21 11:18 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025336 | Abandoned | 2011-12-21 | 2011-12-21 | Manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1293153 | Westbound carriageway west of Murieston Lane. | City of Edinburgh Council |  |  | Yes
2011-12-21 11:07 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025334 | Abandoned | 2011-12-21 | 2011-12-21 | Manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1293128 | Eastbound carriageway west of Murieston Lane. | City of Edinburgh Council |  |  | Yes
2011-12-21 10:58 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025331 | Abandoned | 2011-12-21 | 2011-12-21 | Triple manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1293110 | Eastbound carriageway at junction of McLeod Street. | City of Edinburgh Council |  |  | Yes
2011-12-21 10:47 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025330 | Abandoned | 2011-12-21 | 2011-12-21 | Triple manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1293098 | Eastbound carriageway west of Newton Street. | City of Edinburgh Council |  |  | Yes
2011-12-21 10:37 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025328 | Abandoned | 2011-12-21 | 2011-12-21 | Double manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1293079 | Westbound carriageway east of Tynecastle Terrace. | City of Edinburgh Council |  |  | Yes
2011-12-20 11:14 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025311 | Abandoned | 2011-12-20 | 2011-12-20 | Double manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1292582 | Centre of carriageway at junction of Tynecastle Terrace. | City of Edinburgh Council |  |  | Yes
2011-12-20 11:01 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025310 | Abandoned | 2011-12-20 | 2011-12-20 | Double manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1292549 | Centre of carriageway at junction of Tynecastle Terrace. | City of Edinburgh Council |  |  | Yes
2011-12-20 10:50 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025309 | Abandoned | 2011-12-20 | 2011-12-20 | Manhole cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1292526 | Eastbound carriageway at junction of Wheatfield Street. | City of Edinburgh Council |  |  | Yes
2011-12-20 10:35 | Gorgie Road | Gorgie, Edinburgh | Defective Apparatus | CE001-A000000025307 | Abandoned | 2011-12-20 | 2011-12-20 | Triple cover requires replacement. To be provided to Tarmac by 06/02/2012 for inclusion in capital road maintenance resurfacing programme (Term Service Contract). | City of Edinburgh Council | 1292503 | Eastbound carriageway at junction of Wheatfield Street. | City of Edinburgh Council |  |  | Yes