## Sheet1
APPENDIX 1 - 2023: ANNUAL INDEPENDENT PLAY INSPECTION
HIGH RISK DEFECTS STATUS REPORT
Site Name | Asset Name | Standard Description | Finding Notes | Action | Risk Score | Risk Level | Finding Date | Defect Priority review date by Play team | Priority recommended | Date Approved by Management | Action | Monitoring required | Status | Target Close by Date | Actual Close Date | Target Achieved
Fairmilehead Public Park | General Surface - Grass/Woodchip | Timber is not in good condition. | Edge boarding decayed. | Replace. | 15 | High | 2023-11-23 | 18/12/2023 | Medium | 28-May-2024 | PO raised to replace boarding | Monthly by Park Ranger Team | Closed | 2024-12-17 | 2024-06-20 | yes
Victoria Public Park Play | Barrier - Log | Timber is not in good condition. | Several logs missing. | Replace. | 15 | High | 2023-11-08 | 18/12/2023 | Medium | 28-May-2024 | PO raised to replace barrier log | Monthly by Park Ranger Team | Closed | 2024-12-17 | 2024-06-20 | yes
West Pilton Public Park Senior | Cableway | Timber is not in good condition. | Ramp logs damaged, ply edges damaged. | Replace. | 15 | High | 2023-11-09 | 18/12/2023 | Medium | 28-May-2024 | Cableway disabled | Monthly by Park Ranger Team | Closed | 2024-12-17 | 2024-01-31 | yes
Falcon Road / Park | Multiplay - Playzone | Timber is not in good condition. | Monitor clatter bridge slats. | Read the notes for further action. | 15 | High | 2023-11-01 | 18/12/2023 | Medium | 28-May-2024 | PO raised to replace slats | Monthly by Park Ranger Team | Closed | 2024-12-17 | 2024-06-20 | yes
Note
All high risk assessed defects are reviewed on receipt by the Council's Technical and Play Operational Team. Remediation action and priority is determined based on the defect which is assessed by this team. It should be noted that the risk assessment process is subjective and that actions to remediate high risk defects, identified by an independent inspector, may not be a priority. Approval for this change in priority is authorised by the NES Management team.
Defect 1 - Fairmilehead Public Park | Defect 2 - Victoria Public Park Play | Defect 3 - West Pilton Public Park Senior | Defect 4 - Falcon Road / Park
Formulas:
Target Close by Date = [Defect Priority review date by Play team]+365