## Data1
Start Date | End Date | Local Ref | Activity Reference | Phase Number | Phase Type | Phase Cancelled? | Category | Location | Description | Status | Prom Organisation | Road
2026-06-29 | 29/03/2027 | 3684952 | CE013-S632 | 1 | Asset Activity and Reinstatement if Required | No | Road Restriction | Between the junction with Hanover Street and the junction with Waverley Bridge | Introduction of segregated cycleway on north side of street between South St David Street and Waverley Bridge with associated improvements including alterations to traffic signals and road markings and lining and footway resurfacing where appropriate. Introduction of Tram Only restriction on offside lane on eastbound approach to junction with South St David Street and adjustment of eastbound bus stops between Hanover Street and South St David Street. | Advance Planning | City of Edinburgh Council | Princes Street
2026-09-07 | 20/11/2026 | 4037089 | SW515-MDD/MAC/0009F/BM1 | 1 | Asset Activity and Reinstatement if Required | No | Major | From adjacent to front of Balmoral Hotel to in front of General Register House. | Construction phase to stabilise the ground and fill any voids caused by washout, repair MH9001 and pipeburst the existing pipeline to repair the collapsed section. | Advance Planning | Scottish Water | Princes Street
2026-09-09 | 09/09/2026 | 4012846 | CE003-S45064 | 1 | Asset Activity and Reinstatement if Required | No | Minor Mobile and Short Duration | West Bound - both lanes | Joint Sealant - Night Shift Only - 00.30 to 04.30 | Proposed | City of Edinburgh Council | Princes Street
2026-09-08 | 08/09/2026 | 4012796 | CE003-S45063 | 1 | Asset Activity and Reinstatement if Required | No | Minor Mobile and Short Duration | "West Bound - both lanes Between South St David Stret Junction and National Galeries" | Joint Sealant - Night Shift Only - 00.30 to 04.30 | Proposed | City of Edinburgh Council | Princes Street
2026-09-07 | 07/09/2026 | 4012749 | CE003-S45061 | 1 | Asset Activity and Reinstatement if Required | No | Minor Mobile and Short Duration | "West Bound - both lanes Between Waverly Bridge Junction and South St David Street Junction" | Joint Sealant - Night Shift Only - 00.30 to 04.30 | Proposed | City of Edinburgh Council | Princes Street
2026-07-25 | 06/09/2026 | 4042914 | CE006-L3391 | 1 |  | No | Event | A8 (Princes St to Newbridge Roundabout), A90 (Queensferry Rd to junction with Headrig Rd), Inverleith Row, Montagu Terr, Howard St, Warriston Pl, Huntly St, Canonmills, Belford Rd, Queensferry Terr, Hamilton Pl, Henderson Row, Eyre Pl, Raeburn Pl, Kerr St, St Stephens St, Clarence St, West Silvermills Lane, Silvermills, Henderson Pl Lane, Henderson P, St Vincents Pl, Dundas St, Eyre Terr, Logan St, Eyre Pl Lane, Canon Lane, Canon St, Eyre Cres, Brandon St, Brandon Terr- in each road entirety | Summer Embargo 2026 – No Obstruction on C/W or F/W - A8 from Princes St to Newbridge Roundabout, A90 from Queensferry Road to junction with Headrig Road, Inverleith Row, Montagu Terrace, Howard Street, Warriston Place, Huntly Street, Canonmills, Belford Road, Queensferry Terrace, Hamilton Place, Henderson Row, Eyre Place, Raeburn Place, Kerr Street, St Stephens Street, Clarence Street, West Silvermills Lane, Silvermills, Henderson Place Lane, Henderson Place, St Vincents Place, Dundas Street, Eyre Terrace, Logan Street, Eyre Place Lane, Canon Lane, Canon Street, Eyre Crescent, Brandon Street, Brandon Terrace - in each road entirety from 25 July 2026 to 6 September 2026 | Recorded | City of Edinburgh Council | Princes Street (plus 46 more)
2026-07-25 | 06/09/2026 | 4043006 | CE006-L3400 | 1 |  | No | Event | see Description | Summer Embargo 2026 - No Obstruction on C/W or F/W - Abbey Mount, Abercromby Pl, Ainslie Pl, Antigua St, Atholl Pl, Bank St, Baxter's Pl, Belford Rd, Bellevue, Blair St, Bread St, Bristo Pl, Broughton St, Brunton Pl, Cadzow Pl, Castlehill, Chambers St, Charlotte Sq, Circus Pl, Clifton Terr, Coates Pl, Dean Bridge, Dewar Pl, Douglas Cres, Dundas St, Earl Grey St, East Fountainbridge, East London St, Easter Rd, Elm Row, Forrest Rd, Fountainbridge, Frederick St, George Iv Bridge, George St, Grassmarket, Greenside, Greyfriars Pl, Haddington Pl, Hanover St, Haymarket, High St, Holyrood Rd, Lady Lawson St, Leopold Pl, London St, Lothian Rd, Lynedoch Pl, Montrose Terr, North Bridge, North St Andrew St, Parliament Sq, Picardy Pl, Ponton St, Princes St, Queen St, Queen St Gdns East, Randolph Cliff, Regent Rd, Rutland Pl, Semple St, Shandwick Pl, South Bridge, South Charlotte St, South East Circus Pl, South St Andrew St, Spittal St, St Andrew Sq, St Colme St, St Mary's St, Telford Rd, The Mound, Torphichen Pl, Union Pl, Waterloo Pl, Waverley Bridge, West Maitland St, West Port, York Pl - in each road entirety from 25 July 2026 to 6 September 2026 | Recorded | City of Edinburgh Council | North Bridge (plus 58 more)
2026-03-18 | 31/07/2026 | 3961451 | SW515-MDD/MAC/0708E/BM4 | 1 | Asset Activity and Reinstatement if Required | Yes | Major | Outside General Register House | Construction phase to stabilise the ground and fill any voids caused by washout, repair MH9001 and pipeburst the existing pipeline to repair the collapsed section. | Abandoned | Scottish Water | Princes Street
2026-05-24 | 24/05/2026 | 3910190 | CE006-L3089 | 1 |  | No | Event | Buccleuch Pl, In its entirety (Access for event buses only).Lauriston Pl, From the east kerbline of the entrance to George Heriot’s school to Forrest Rd. George IV Br, In its entirety. Lawnmarket, In its entirety. Bank St, In its entirety. N. Bank St, In its entirety. The Mound, In its entirety. Mound Pl, In its entirety. Hanover St, Southbound between Rose St and Princes St. Cockburn St, Waverley Br, Market St, Jeffrey St, Canongate and Abbey Strand In their entirety. | Edinburgh Marathon Festival 2026 - Road Closure - Buccleuch Place, Lauriston Place, George IV Bridge, Lawnmarket, Bank Street, North Bank Street, The Mound, Mound Place, Hanover Street, Cockburn Street, Waverley Bridge, Market Street, Jeffrey Street, Canongate, Abbey Strand – From 06.00hrs to 11.00hrs on 24 May 2026 - Buccleuch Place From 05.00hrs to 12.30hrs on 24 May 2026 | Recorded | City of Edinburgh Council | Buccleuch Place (plus 15 more)
2026-05-24 | 24/05/2026 | 3910238 | CE006-L3090 | 1 |  | No | Temporary Traffic Restriction | Buccleuch Pl, In its entirety (Access for event buses only).Lauriston Pl, From the east kerbline of the entrance to George Heriot’s school to Forrest Rd. George IV Br, In its entirety. Lawnmarket, In its entirety. Bank St, In its entirety. N. Bank St, In its entirety. The Mound, In its entirety. Mound Pl, In its entirety. Hanover St, Southbound between Rose St and Princes St. Cockburn St, Waverley Br, Market St, Jeffrey St, Canongate and Abbey Strand In their entirety. | Edinburgh Marathon Festival 2026 - Road Closure - Buccleuch Place, Lauriston Place, George IV Bridge, Lawnmarket, Bank Street, North Bank Street, The Mound, Mound Place, Hanover Street, Cockburn Street, Waverley Bridge, Market Street, Jeffrey Street, Canongate, Abbey Strand – From 06.00hrs to 11.00hrs on 24 May 2026 - Buccleuch Place From 05.00hrs to 12.30hrs on 24 May 2026 | Recorded | City of Edinburgh Council | Buccleuch Place (plus 15 more)
2025-05-16 | 15/05/2026 | 3814012 | CE021-STARBUCKS551044 | 1 |  | No | Permission | 118, PRINCES STREET, PRINCES STREET, NEW TOWN, EDINBURGH, EH2 4AA | Starbucks Coffee | Commenced | City of Edinburgh Council | Princes Street
2026-05-04 | 11/05/2026 | 3989902 | SP100-2101955251-01 | 1 | Asset Activity and Reinstatement if Required | No | Standard | O/S No120b, Princes Street, New Town, Edinburgh | Exc, 1x J/B, and install cable | Advance Planning | SP Energy Networks | Princes Street
2026-04-23 | 24/04/2026 | 4038557 | CE003-S45139 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Lane 1 closures both directions | Road Surfacing Works - overnight works | Proposed | City of Edinburgh Council | Princes Street
2026-04-22 | 23/04/2026 | 4038386 | CE003-S45138 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Princes Street / Lothian Road Junction | Road Surfacing Works - overnight works | Proposed | City of Edinburgh Council | Princes Street
2026-04-21 | 22/04/2026 | 4038293 | CE003-S45137 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Lane 1 closures both directions - overnight works | Road Surfacing Works | Proposed | City of Edinburgh Council | Princes Street
2026-04-20 | 21/04/2026 | 4035551 | CE003-S45136 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Lane 2 closure Westbound | Concrete repair to trackform - overnight works | Proposed | City of Edinburgh Council | Princes Street
2026-04-16 | 17/04/2026 | 4035402 | CE003-S45134 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Westbound Direction, contraflow system | Concrete Repairs to Tramway | Proposed | City of Edinburgh Council | Princes Street
2026-04-09 16:10 | 16/04/2026 | 4040825 | SW100-10380686/CSD | 1 | Asset Activity and Reinstatement if Required | No | Urgent | The Works Store, 120A Princes Street Edinburgh EH2 4AD | Stoptap to be made accessible Water flooding basement of shop | Closed No Excavation | Scottish Water | Princes Street
2026-04-13 22:10 | 14/04/2026 | 4035159 | CE003-S45131 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Princes Street (after South Charlotte Street junction) | Replacement of Duct Chamber Cover - overnight works | Closed | City of Edinburgh Council | Princes Street
2026-04-13 15:19 | 13/04/2026 | 4043046 | SW100-3944970 | 1 |  | No | Accepted Works | On the westbound carriageway on the pedestrian crossing outside Waverley Mall, opposite no 24 / 25 Black sheep coffee shop | 1no sunken manhole between studded area of pedestrian crossing. Been raised several times over the last few years but no action has been taken. | Accepted | Scottish Water | Princes Street
2026-04-13 00:30 | 13/04/2026 | 4034900 | CE003-S45130 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Lane 2 closure Westbound | Replacement of Duct Chamber Cover - overnight works | Closed | City of Edinburgh Council | Princes Street
2026-04-09 23:59 | 10/04/2026 | 4034824 | CE003-S45128 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Lane 1 closure Westbound - overnight works | Replacement of Duct Chamber Cover | Closed | City of Edinburgh Council | Princes Street
2026-04-09 23:59 | 10/04/2026 | 4034882 | CE003-S45129 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Lane 1 closure Westbound | Replacement of Duct Chamber Cover - overnight works | Closed | City of Edinburgh Council | Princes Street
2026-04-07 23:59 | 08/04/2026 | 4034630 | CE003-S45127 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Lane 2 closure Westbound - overnight works | Concrete repair to trackform | Closed | City of Edinburgh Council | Princes Street
2026-04-07 23:59 | 08/04/2026 | 4034596 | CE003-S45126 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Lane 2 Westbound, near Lothian Road junction - overnight works | Concrete Repairs to Tramway | Closed | City of Edinburgh Council | Princes Street
2026-04-04 | 04/04/2026 | 4036343 | CE006-L3358 | 1 |  | No | Event | The Mound from south exit from Mound Precinct to Princes Street, Princes Street from the Mound to Hanover Street, Hanover Street from Princes Street to George Street, George Street from Hanover Street to South St David Street, South St David Street from George Street to Princes Street, Princes Street from South St David Street to Waterloo Place, Waterloo Place in its entirety, Regent Road From Waterloo Place to Regent Terrace and Regent Terrace in its entirety. | Support Palestine March. 4 April 2026 from 13:00 to 16:00. Stop/Go Boards Traffic Control with a ‘rolling closure’ for a short period within the times stated. From The Mound, Princes Street, Hanover Street, George Street, South St David Street, Princes Street, Waterloo Place, Regent Road and Regent Terrace. | Completed | City of Edinburgh Council | The Mound (plus 7 more)
2026-03-28 06:30 | 28/03/2026 | 4010130 | CE013-S1073 | 1 | Asset Activity and Reinstatement if Required | No | Minor Mobile and Short Duration | On the pavement, outside 137, 138 Princes St., Edinburgh EH2 4BL | Installation of Bike parking racks, minor civil works (coring). | Closed No Excavation | City of Edinburgh Council | Princes Street
2026-03-26 22:20 | 27/03/2026 | 4025042 | CE003-S45121 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Eastbound at Castle Street | Replacement of duct chamber cover. Overnight working. | Closed | City of Edinburgh Council | Princes Street
2026-03-25 22:15 | 26/03/2026 | 4025024 | CE003-S45120 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Westbound at St John's Church | Replacement of duct chamber cover. Overnight working. | Closed | City of Edinburgh Council | Princes Street
2026-03-10 | 23/03/2026 | 3988491 | SP601-2101370915/PRIN | 1 | Asset Activity and Reinstatement if Required | Yes | Standard | O/S 1 | Excavate, backfill and reinstate to disconnect supply to Street Light pillar | Abandoned | SP Energy Networks | Princes Street
2026-03-21 | 21/03/2026 | 3993937 | CE006-L3269 | 1 |  | No | Event | Princes Street, North Bridge to Leith Street. | Walk for a Bloke (Charity Walk) 2026 - No Obstruction on C/W or F/W - On footways & off-street where possible - Princes Street - from 06.00hrs to 15.00hrs on Saturday 21 March 2026 - For full map click below: https://footpathapp.com/routes/8f874e4e-6af4-4e1a-8a39-8e81fecbdd3f | Completed | City of Edinburgh Council | Princes Street
2026-03-20 07:30 | 20/03/2026 | 3540205 | SP200-992893S | 3 | Remedial Reinstatement | No | Remedial Other | o/s no 54 | Remedial - make good 12 slabs to be lifted, re-laid and pointed | Closed | SP Energy Networks | Princes Street
2026-03-19 10:00 | 20/03/2026 | 3820673 | SP302-2101582777 | 3 | Remedial Reinstatement | No | Remedial Other | O/S 108 | ***DEFECT REPAIR - REPOINT SLABS*** excavate backfill and reinstate 3 x jointbays for 3 x LV pot end cables | Closed | SP Energy Networks | Princes Street
2026-03-20 00:30 | 20/03/2026 | 4024591 | CE008-S1855 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Between South St David Street and The Mound. Westbound inside lane. | Carriageway patching due to the rapidly deteriorating carriageway. Night working: 0030 to 0430 | Closed | City of Edinburgh Council | Princes Street
2026-03-13 00:15 | 13/03/2026 | 3315337 | SW100-08223307/LWS-IW | 5 | Remedial Reinstatement | No | Remedial Other | Junction with Hanover street | 2 sunken sv valves on cw | Closed | Scottish Water | Princes Street
2026-03-09 11:45 | 09/03/2026 | 3820673 | SP302-2101582777 | 2 | Remedial Reinstatement | No | Remedial Other | O/S 108 | ***DEFECT REPAIR - REPOINT SLABS*** excavate backfill and reinstate 3 x jointbays for 3 x LV pot end cables | Closed | SP Energy Networks | Princes Street
2026-02-28 | 28/02/2026 | 3988319 | BT038-BTTEF3532-P120998-E | 1 | Asset Activity and Reinstatement if Required | Yes | Minor Without Excavation | In footway opp. no. 97-98 Princes Street. | Installation of 4G/5G small cell telecommunications equipment on the CCTV column to enhance mobile network coverage in the area. The works will be carried out using a scissor lift positioned in the lane adjacent to the CCTV column, located more than 4m from the tram lines. The scissor lift will be operated only for vertical (up-and-down) movement to prevent accidental lateral motion, ensuring safe operation near the tram infrastructure. The vehicle transporting the scissor lift will be parked on-site within the traffic management plan. All work will be conducted between 00:00 - 04:00, to minimise risk and disruption to tram services. | Abandoned | BT | Princes Street
2026-02-27 | 27/02/2026 | 4009106 | CE008-S1829 | 1 | Asset Activity and Reinstatement if Required | No | Urgent | From west side crossing at Frederick Street to The Mound. Within westbound inside lane. | Carriageway patching due to the rapidly deteriorating carriageway. Night working: 0030 to 0430 | Closed | City of Edinburgh Council | Princes Street
2026-02-26 11:59 | 27/02/2026 | 3983603 | BT038-103848-P120999-NP | 1 | Asset Activity and Reinstatement if Required | Yes | Standard | Activities in the footway in front of Statue of Thomas Guthrie. Opposite Castle Street. | Installation of 4G/5G small cell telecommunications equipment on the CCTV column to enhance mobile network coverage in the area. | Abandoned | BT | Princes Street
2026-02-23 12:09 | 23/02/2026 | 4006374 | CE001-A67210 | 1 |  | No | Defective Apparatus | Outside number 135 | Sunken loose and noisy manhole cover on carriageway | Awaiting Response | City of Edinburgh Council | Princes Street
2026-02-08 07:54 | 22/02/2026 | 3994623 | SP200-1305589S | 1 | Asset Activity and Reinstatement if Required | No | Emergency | outside 46 | Excavate to repair LV fault. Vulnerable customers may be impacted by these works, hence why they have been raised under the Emergency Notice type. Should you require further information, please contact Reporting@spenergynetworks.co.uk | Closed | SP Energy Networks | Princes Street
2026-02-20 | 20/02/2026 | 4003507 | CE008-S1820 | 1 | Asset Activity and Reinstatement if Required | No | Urgent | Westbound from The Mound to Frederick Street. C/W | Carriageway patching due to the rapidly deteriorating carriageway. Night working: 0030 to 0430 | Closed | City of Edinburgh Council | Princes Street
2026-02-16 22:10 | 18/02/2026 | 3981294 | CE013-S1002 | 1 | Asset Activity and Reinstatement if Required | No | Minor Mobile and Short Duration | Princes Street between tram stop and Royal Scottish Academy C/way | Lifting of manhole covers and recording of video footage of inside the manhole Night shift | Closed No Excavation | City of Edinburgh Council | Princes Street
2026-02-13 | 17/02/2026 | 2985686 | SW100-07750062/LWS-IW | 6 | Remedial Reinstatement | Yes | Remedial Other | Outside Primark on eastbound lane | 1no low fire hydrant also cracking and potholed asphalt in previous reinstatement (RU: Utility Apparatus) | Closed | Scottish Water | Princes Street
2026-02-04 23:30 | 05/02/2026 | 3984669 | CE003-S45057 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Lane 2 westbound, near South Charlotte Street junction. | Concrete repair to track form, nearside shoulder. Nightshift working. | Closed | City of Edinburgh Council | Princes Street
2026-02-04 00:10 | 04/02/2026 | 3984635 | CE003-S45055 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Lane 2 eastbound, near South Charlotte Street junction. | Concrete repair to track form, nearside shoulder. Nightshift working. | Closed | City of Edinburgh Council | Princes Street
2026-02-02 22:10 | 03/02/2026 | 3984619 | CE003-S45054 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Lane 1 eastbound, opposite Princes Street tram stop. | Resurfacing to duct chamber. Nightshift working. | Closed | City of Edinburgh Council | Princes Street
2026-01-30 00:15 | 30/01/2026 | 3905460 | SW100-NRSWA-16767/LWS-IW | 2 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | On the westbound carriageway at the junction with Waverley Bridge | Sunken SV box (RU: Utility Apparatus) | Closed | Scottish Water | Princes Street
2026-01-23 00:15 | 23/01/2026 | 3824241 | SW100-NRSWA-12805/LWS-IW | 3 | Asset Activity and Reinstatement if Required | No | Major | Westbound outside Costa Coffee at Waverley Mall | Sunken carriageway manhole | Closed | Scottish Water | Princes Street
2026-01-20 11:12 | 20/01/2026 | 3979632 | CE001-A67132 | 1 |  | Yes | Defective Apparatus | On the footway opposite no100 | Water coming out from joint in flagged footway | Abandoned | City of Edinburgh Council | Princes Street
2026-01-12 09:45 | 12/01/2026 | 3540205 | SP200-992893S | 2 | Remedial Reinstatement | No | Remedial Other | o/s no 54 | Remedial - make good 12 slabs to be lifted, re-laid and pointed | Closed | SP Energy Networks | Princes Street
2026-01-12 09:45 | 12/01/2026 | 3270007 | SP200-646569F | 3 | Remedial Reinstatement | No | Remedial Other | Outside no 99 Princes St | Remedial - Lift and relay 3 tactile slabs | Closed | SP Energy Networks | Princes Street
2025-11-27 | 05/01/2026 | 3905122 | CE006-L3028 | 1 |  | No | Event | A8 (Princes St to Newbridge Roundabout), A90 (Queensferry Rd to junction with Headrig Rd), Inverleith Row, Montagu Terr, Howard St, Warriston Pl, Huntly St, Canonmills, Belford Rd, Queensferry Terr, Hamilton Pl, Henderson Row, Eyre Pl, Raeburn Pl, Kerr St, St Stephens St, Clarence St, West Silvermills Lane, Silvermills, Henderson Pl Lane, Henderson P, St Vincents Pl, Dundas St, Eyre Terr, Logan St, Eyre Pl Lane, Canon Lane, Canon St, Eyre Cres, Brandon St, Brandon Terr- in each road entirety | Winter Embargo 2025 – No Obstruction on C/W or F/W - A8 from Princes St to Newbridge Roundabout, A90 from Queensferry Road to junction with Headrig Road, Inverleith Row, Montagu Terrace, Howard Street, Warriston Place, Huntly Street, Canonmills, Belford Road, Queensferry Terrace, Hamilton Place, Henderson Row, Eyre Place, Raeburn Place, Kerr Street, St Stephens Street, Clarence Street, West Silvermills Lane, Silvermills, Henderson Place Lane, Henderson Place, St Vincents Place, Dundas Street, Eyre Terrace, Logan Street, Eyre Place Lane, Canon Lane, Canon Street, Eyre Crescent, Brandon Street, Brandon Terrace - in each road entirety from 27 November 2025 to 5 January 2026 | Completed | City of Edinburgh Council | Princes Street (plus 46 more)
2025-11-27 | 05/01/2026 | 3919103 | CE006-L3133 | 1 |  | No | Event | see Description | Winter Embargo 2025 - No Obstruction on C/W or F/W - Abbey Mount, Abercromby Pl, Ainslie Pl, Antigua St, Atholl Pl, Bank St, Baxter's Pl, Belford Rd, Bellevue, Blair St, Bread St, Bristo Pl, Broughton St, Brunton Pl, Cadzow Pl, Castlehill, Chambers St, Charlotte Sq, Circus Pl, Clifton Terr, Coates Pl, Dean Bridge, Dewar Pl, Douglas Cres, Dundas St, Earl Grey St, East Fountainbridge, East London St, Easter Rd, Elm Row, Forrest Rd, Fountainbridge, Frederick St, George Iv Bridge, George St, Grassmarket, Greenside, Greyfriars Pl, Haddington Pl, Hanover St, Haymarket, High St, Holyrood Rd, Lady Lawson St, Leopold Pl, London St, Lothian Rd, Lynedoch Pl, Montrose Terr, North Bridge, North St Andrew St, Parliament Sq, Picardy Pl, Ponton St, Princes St, Queen St, Queen St Gdns East, Randolph Cliff, Regent Rd, Rutland Pl, Semple St, Shandwick Pl, South Bridge, South Charlotte St, South East Circus Pl, South St Andrew St, Spittal St, St Andrew Sq, St Colme St, St Mary's St, Telford Rd, The Mound, Torphichen Pl, Union Pl, Waterloo Pl, Waverley Bridge, West Maitland St, West Port, York Pl - in each road entirety from 27 November 2025 to 5 January 2026 | Completed | City of Edinburgh Council | North Bridge (plus 58 more)
2025-12-15 22:00 | 16/12/2025 | 3933567 | VF047-KMV1990 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | o/s 2 | Planned Vodafone outage, access chamber to carryout joint exchange | Closed No Excavation | Vodafone Limited | Princes Street
2025-12-08 11:58 | 14/12/2025 | 3954948 | SP200-1271293S | 1 | Asset Activity and Reinstatement if Required | No | Emergency | O/S NO. 46 | Excavate to repair l/v fault. Vulnerable customers may be impacted by these works, hence why they have been raised under the Emergency Notice type. Should you require further information, please contact Reporting@spenergynetworks.co.uk | Closed | SP Energy Networks | Princes Street
2025-11-26 | 29/11/2025 | 3824241 | SW100-NRSWA-12805/LWS-IW | 2 | Asset Activity and Reinstatement if Required | Yes | Major | Westbound outside Costa Coffee at Waverley Mall | Sunken carriageway manhole | Accepted | Scottish Water | Princes Street
2025-11-28 00:30 | 28/11/2025 | 3946070 | CE003-S45052 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Westbound lane 1 closure at the Mound Princes Street adjacent to Princes Street tram stop. Traffic to share tram lane. | Emergency surfacing repairs to buried chamber cover on c/way. Nightshift from 11pm until 4:30am. | Closed | City of Edinburgh Council | Princes Street
2025-11-27 10:24 | 27/11/2025 | 3947733 | SW100-3944957 | 1 |  | No | Accepted Works | On the eastbound carriageway outside Popeyes | Sunken and loose fire hydrant | Accepted | Scottish Water | Princes Street
2025-11-24 14:41 | 24/11/2025 | 3944970 | CE001-A67006 | 1 |  | No | Defective Apparatus | On the westbound carriageway on the pedestrian crossing outside Waverley Mall, opposite no 24 / 25 Black sheep coffee shop | 1no sunken manhole between studded area of pedestrian crossing. Been raised several times over the last few years but no action has been taken. | Accepted | City of Edinburgh Council | Princes Street
2025-11-24 14:30 | 24/11/2025 | 3944957 | CE001-A67005 | 1 |  | No | Defective Apparatus | On the eastbound carriageway outside Popeyes | Sunken and loose fire hydrant | Accepted | City of Edinburgh Council | Princes Street
2025-11-07 19:30 | 07/11/2025 | 2985686 | SW100-07750062/LWS-IW | 5 | Remedial Reinstatement | Yes | Remedial Other | Outside Primark on eastbound lane | 1no low fire hydrant also cracking and potholed asphalt in previous reinstatement (RU: Utility Apparatus) | Closed | Scottish Water | Princes Street
2025-11-07 19:30 | 07/11/2025 | 2721523 | SW100-07037556/LWS | 3 | Remedial Reinstatement | Yes | Remedial Other | 118 PRINCESS STREET, EDINBURGH | REPAIR DANGEROUS SUNKEN FIRE HYDRANT | Closed | Scottish Water | Princes Street
2025-11-03 07:33 | 06/11/2025 | 3907978 | CE016-S2688 | 1 | Asset Activity and Reinstatement if Required | No | Standard | OS 101-103 F/Way | REMOVE AND REPLACE PARKING SIGN AND SUPPORT | Closed | City of Edinburgh Council | Princes Street
2025-10-27 08:07 | 30/10/2025 | 3896144 | CE016-S2640 | 1 | Asset Activity and Reinstatement if Required | No | Standard | OPP 87 | REMOVE PARKING SIGN AND SUPPORT | Closed | City of Edinburgh Council | Princes Street
2025-10-09 08:00 | 22/10/2025 | 3893501 | SP202-2101619928 | 1 | Asset Activity and Reinstatement if Required | No | Standard | O/S 105 | Excavate, backfill & reinstate for disconnection of LV service | Closed | SP Energy Networks | Princes Street
2025-10-16 23:30 | 17/10/2025 | 3908592 | CE003-S45034 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Road narrowing/lane closure at Eastbound merge on Princes Street near South Saint Andrew Street junction - C/way | Tramway concrete and adjacent surfacing repairs - 11:30pm until 4:30am Nightshift working only. No impact on tram running | Closed | City of Edinburgh Council | Princes Street
2025-10-15 23:00 | 16/10/2025 | 3908582 | CE003-S45033 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Westbound, Lane 2 & 3 closure on Princes Street just west of South Charlotte St Junction - C/way | Tramway repairs including works to duct chambers - 11pm until 5:00am Nightshift working only, no impact on tram running | Closed | City of Edinburgh Council | Princes Street
2025-10-14 23:30 | 15/10/2025 | 3908336 | CE003-S45029 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Westbound, Lane 1 closure on Princes Street just west of Castle street - C/way | Tramway repairs including works to duct chambers - 11pm until 4:30am Nightshift working only, no impact on tram running | Closed | City of Edinburgh Council | Princes Street
2025-10-13 23:30 | 14/10/2025 | 3908322 | CE003-S45028 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Eastbound, Lane 1 closure just East of Castle Street - C/way | Tramway repairs including works to duct chambers - 11:15pm until 4:30am Nightshift working only, no impact on tram running | Closed | City of Edinburgh Council | Princes Street
2025-10-13 00:30 | 13/10/2025 | 3908308 | CE003-S45027 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Westbound, Lane 1 closure on Princes Street just west of the tramstop - C/way | Tramway repairs including works to duct chambers - 11pm until 5:00am Nightshift working only, no impact on tram running | Closed | City of Edinburgh Council | Princes Street
2025-10-10 00:15 | 10/10/2025 | 3315337 | SW100-08223307/LWS-IW | 4 | Remedial Reinstatement | No | Remedial Other | Junction with Hanover street | 2 sunken sv valves on cw | Closed | Scottish Water | Princes Street
2025-10-09 09:09 | 09/10/2025 | 3914026 | SW100-3913826 | 1 |  | No | Accepted Works | On the carriageway at bus stop PK | Sunken fire hydrant (RU: Utility Apparatus) | Accepted | Scottish Water | Princes Street
2025-10-08 15:53 | 08/10/2025 | 3913826 | CE001-A66881 | 1 |  | No | Defective Apparatus | On the carriageway at bus stop PK | Sunken fire hydrant (RU: Utility Apparatus) | Accepted | City of Edinburgh Council | Princes Street
2025-10-05 | 05/10/2025 | 2920700 | SP202-2100709295B | 5 | Interim to Permanent Reinstatement | Yes | Minor With Excavation | FROM NO.31 TO JUNCTION OF | Remove TEMP Material and replace with new channel drains | Cleared | SP Energy Networks | Princes Street
2025-10-02 23:00 | 03/10/2025 | 3900151 | CE003-S45025 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Both directions between the Lothian Road and South Charlotte Street junctions | Concrete repairs to tramway. Overnight working. | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-10-01 23:10 | 02/10/2025 | 3900122 | CE003-S45024 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Eastbound adjacent to Princes Street tram stop | Duct chamber cover repairs for tramway. Overnight working. | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-09-30 23:10 | 01/10/2025 | 3900065 | CE003-S45023 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Westbound opposite South Charlotte street junction. | Concrete repairs to tramway. Overnight working. | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-09-29 22:20 | 30/09/2025 | 3900037 | CE003-S45022 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Adjacent to Princes Street tram stop. | Duct chamber cover repairs for tramway. Overnight working. | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-09-28 22:55 | 29/09/2025 | 3899890 | CE003-S45021 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Both directions between The Mound and South Charlotte street junction on tramway. | Concrete repairs to tramway. Overnight working. | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-09-26 10:46 | 26/09/2025 | 3905460 | SW100-NRSWA-16767/LWS-IW | 1 |  | No | Accepted Works | On the westbound carriageway at the junction with Waverley Bridge | Sunken SV box (RU: Utility Apparatus) | Accepted | Scottish Water | Princes Street
2025-09-25 14:36 | 25/09/2025 | 3904983 | CE001-A66859 | 1 |  | No | Defective Apparatus | On the westbound carriageway at the junction with Waverley Bridge | Sunken SV box (RU: Utility Apparatus) | Accepted | City of Edinburgh Council | Princes Street
2025-09-24 20:20 | 25/09/2025 | 3888871 | VF047-KMV1891 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | J/W Leith Street | non-excavation. access CW chamber to carry out fibre prove | Closed No Excavation | Vodafone Limited | Princes Street
2025-09-13 | 13/09/2025 | 3896537 | CE006-L3005 | 1 |  | No | Temporary Traffic Restriction | Waverley Bridge, In its entirety. Market Street, From Waverley Bridge to East Market Street. East Market Street, In its entirety. New Street, From East Market Street to Canongate. Canongate, From New Street to Horse Wynd. Horse Wynd, In its entirety. | Support Palestine - Stop/Go Boards Traffic Control - Waverley Bridge, In its entirety. Market Street, From Waverley Bridge to East Market Street. East Market Street, In its entirety. New Street, From East Market Street to Canongate. Canongate, From New Street to Horse Wynd. Horse Wynd, In its entirety. From Saturday 13 September 2025 at 13:30pm to Saturday 13 September 2025 at 15:30pm. | Completed | City of Edinburgh Council | Waverley Bridge (plus 7 more)
2025-07-26 | 07/09/2025 | 3788230 | CE006-L2545 | 1 |  | No | Event | see Description | Summer Embargo 2025 - No Obstruction on C/W or F/W - Abbey Mount, Abercromby Pl, Ainslie Pl, Antigua St, Atholl Pl, Bank St, Baxter's Pl, Belford Rd, Bellevue, Blair St, Bread St, Bristo Pl, Broughton St, Brunton Pl, Cadzow Pl, Castlehill, Chambers St, Charlotte Sq, Circus Pl, Clifton Terr, Coates Pl, Dean Bridge, Dewar Pl, Douglas Cres, Dundas St, Earl Grey St, East Fountainbridge, East London St, Easter Rd, Elm Row, Forrest Rd, Fountainbridge, Frederick St, George Iv Bridge, George St, Grassmarket, Greenside, Greyfriars Pl, Haddington Pl, Hanover St, Haymarket, High St, Holyrood Rd, Lady Lawson St, Leopold Pl, London St, Lothian Rd, Lynedoch Pl, Montrose Terr, North Bridge, North St Andrew St, Parliament Sq, Picardy Pl, Ponton St, Princes St, Queen St, Queen St Gdns East, Randolph Cliff, Regent Rd, Rutland Pl, Semple St, Shandwick Pl, South Bridge, South Charlotte St, South East Circus Pl, South St Andrew St, Spittal St, St Andrew Sq, St Colme St, St Mary's St, Telford Rd, The Mound, Torphichen Pl, Union Pl, Waterloo Pl, Waverley Bridge, West Maitland St, West Port, York Pl - in each road entirety from 26th July 2025 - 7th September 2025 | Completed | City of Edinburgh Council | North Bridge (plus 58 more)
2025-07-26 | 07/09/2025 | 3787793 | CE006-L2540 | 1 |  | No | Event | A8 (Princes St to Newbridge Roundabout), A90 (Queensferry Rd to junction with Headrig Rd), Inverleith Row, Montagu Terr, Howard St, Warriston Pl, Huntly St, Canonmills, Belford Rd, Queensferry Terr, Hamilton Pl, Henderson Row, Eyre Pl, Raeburn Pl, Kerr St, St Stephens St, Clarence St, West Silvermills Lane, Silvermills, Henderson Pl Lane, Henderson P, St Vincents Pl, Dundas St, Eyre Terr, Logan St, Eyre Pl Lane, Canon Lane, Canon St, Eyre Cres, Brandon St, Brandon Terr- in each road entirety | Summer Embargo 2025 – No Obstruction on C/W or F/W - A8 from Princes St to Newbridge Roundabout, A90 from Queensferry Road to junction with Headrig Road, Inverleith Row, Montagu Terrace, Howard Street, Warriston Place, Huntly Street, Canonmills, Belford Road, Queensferry Terrace, Hamilton Place, Henderson Row, Eyre Place, Raeburn Place, Kerr Street, St Stephens Street, Clarence Street, West Silvermills Lane, Silvermills, Henderson Place Lane, Henderson Place, St Vincents Place, Dundas Street, Eyre Terrace, Logan Street, Eyre Place Lane, Canon Lane, Canon Street, Eyre Crescent, Brandon Street, Brandon Terrace - in each road entirety from from 26 July 2025 to 7 September 2025 | Completed | City of Edinburgh Council | Princes Street (plus 46 more)
2025-08-30 | 30/08/2025 | 3879620 | CE006-L2978 | 1 |  | No | Event | The Mound, From Mound Precinct west exit to Princes Street. Princes Street, From The Mound to Hanover Street. Hanover Street, From Princes Street to George Street. George Street, From Hanover Street to Charlotte Square. Charlotte Square, West leg from George Street to Charlotte Square south leg. Charlotte Square South leg in its entirety. | Support Palestine Event - Stop/Go Boards Traffic Control - The Mound, Princes Street, Hanover Street, George Street, Charlotte Square from 13:00hours to 15:00hours on 30 August 2025. | Completed | City of Edinburgh Council | The Mound (plus 5 more)
2025-08-30 | 30/08/2025 | 3879622 | CE006-L2979 | 1 |  | No | Temporary Traffic Restriction | The Mound, From Mound Precinct west exit to Princes Street. Princes Street, From The Mound to Hanover Street. Hanover Street, From Princes Street to George Street. George Street, From Hanover Street to Charlotte Square. Charlotte Square, West leg from George Street to Charlotte Square south leg. Charlotte Square South leg in its entirety. | Support Palestine Event - Stop/Go Boards Traffic Control - The Mound, Princes Street, Hanover Street, George Street, Charlotte Square from 13:00hours to 15:00hours on 30 August 2025. | Completed | City of Edinburgh Council | The Mound (plus 5 more)
2025-08-28 | 28/08/2025 | 3877532 | CE006-L2970 | 1 |  | No | Event | Lochside Cres & Edinburgh Park in their entirety, South Gyle B/way from Edinburgh Park to Glasgow Rd, Glasgow Rd, St Johns Rd, Corstorphine Rd, Roseburn Terr, West Coates, Haymarket Terr, Coates Pl & Shandwick Pl all in their entirety, Princes St from Shandwick Pl to Frederick St, Frederick St from Princes St to George St, George St from Frederick St to St Andrew Sq, St Andrew Sq, The Mound, Market St & East Market St in their entirety. | Edinburgh's Private Hire Vehicles Go Slow Protest. Rolling closures for short periods within the times 10:00 to 11:30 affecting Lochside Crescent, Edinburgh Park, South Gyle Broadway, Glasgow Road, St Johns Road, Corstorphine Road, Roseburn Terrace, West Coates, Haymarket Terrace, Coates Place, Shandwick Place, Princes Street, Frederick Street, George Street, St Andrew Square, The Mound, Market Street and East Market Street. | Completed | City of Edinburgh Council | Lochside Crescent (plus 21 more)
2025-08-19 15:58 | 22/08/2025 | 3879598 | SP200-1205647S/A | 1 | Asset Activity and Reinstatement if Required | No | Emergency | Side of 77 | Excavate to repair LV fault | Closed No Excavation | SP Energy Networks | Princes Street
2025-07-21 08:14 | 24/07/2025 | 3838666 | CE016-S2452 | 1 | Asset Activity and Reinstatement if Required | No | Standard | OPP HMV AT FRONT OF FOOTWAY | REMOVE PARKING SIGN AND SUPPORT | Closed | City of Edinburgh Council | Princes Street
2025-07-01 07:30 | 21/07/2025 | 3820673 | SP302-2101582777 | 1 | Asset Activity and Reinstatement if Required | No | Standard | O/S 108 | excavate backfill and reinstate 3 x jointbays for 3 x LV pot end cables | Closed | SP Energy Networks | Princes Street
2025-07-21 00:30 | 21/07/2025 | 3855613 | CE003-S44976 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Between Lothian Rd and Shandwick Place westbound. | Cup welds and grinding. Overnight works. | Closed | City of Edinburgh Council | Princes Street
2025-07-19 | 19/07/2025 | 3856559 | CE006-L2841 | 1 |  | Yes | Event | Princes St from Mound to Hanover St, Hanover St in entirety, Queen St Gdns East in entirety, Dundas St from Queen St Gdns East to Northumberland St, Northumberland St from Dundas St to Howe St, Howe St from Northumberland St to Queen St Gdns West, Queen St Gdns West in entirety, Frederick St from Queen St Gdns West to George St, George St from Frederick St to Charlotte Sq, Charlotte Sq west leg from George St to north leg. | Support Palestine Event. Stop/Go Boards Traffic Control on Princes St from Mound to Hanover St, Hanover St in entirety, Queen St Gdns East in entirety, Dundas St from Queen St Gdns East to Northumberland St, Northumberland St from Dundas St to Howe St, Howe St from Northumberland St to Queen St Gdns West, Queen St Gdns West in entirety, Frederick St from Queen St Gdns West to George St, George St from Frederick St to Charlotte Sq, Charlotte Sq west leg from George St to north leg from 13:30 to 15:30 on 19 July 2025. | Abandoned | City of Edinburgh Council | Princes Street (plus 5 more)
2025-07-16 00:30 | 16/07/2025 | 3851352 | CE003-S44974 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | Tramway closure only between The Mound and Frederick Street westbound. | Tramway maintenance works. Overnight works. | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-07-15 00:29 | 15/07/2025 | 3851310 | CE003-S44973 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | Tramway closure only between Castle Street and South Charlotte Street west bound. | Tramway maintenance works. Overnight works. | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-07-14 00:25 | 14/07/2025 | 3847165 | CE003-S44972 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Tramway closure only between Frederick Street and Castle Street west bound. | Tramway maintenance works. Overnight works. | Closed | City of Edinburgh Council | Princes Street
2025-07-11 00:15 | 12/07/2025 | 3566256 | SW100-08613199/LWS-IW | 4 | Asset Activity and Reinstatement if Required | No | Major | At the junction with South St David Street | 2 no sunken SV boxes | Closed | Scottish Water | Princes Street
2025-07-08 20:00 | 08/07/2025 | 3851894 | SW100-9044367/CLANCY | 1 | Asset Activity and Reinstatement if Required | No | Urgent | FROM NO 99-117 | URGENT - CCTV & Vactoring | Closed No Excavation | Scottish Water | Princes Street
2025-06-25 01:00 | 03/07/2025 | 3820447 | SW100-8975774/CLANCY | 1 | Asset Activity and Reinstatement if Required | No | Standard | OS NO 25 | Sewer R&M | Closed No Excavation | Scottish Water | Princes Street
2025-06-30 06:05 | 03/07/2025 | 3825497 | CE016-S2443 | 1 | Asset Activity and Reinstatement if Required | No | Standard | OS 87 (ANN SUMMERS) AT FRONT OF FOOTWAY | REMOVE PARKIING SIGN AND SUPPORT | Closed | City of Edinburgh Council | Princes Street
2025-06-28 | 28/06/2025 | 3843888 | CE006-L2728 | 1 |  | No | Temporary Traffic Restriction | Princes Street from The Mound to Leith Street; Waterloo Place in its entirety, Regent Road from Waterloo Place to Regent Terrace; Regent Terrace outside the United States Consulate | Stop the War Coalition March - Road Closures under Police Stop and Hold for a short period within stated times - Princes Street, Waterloo Place, Regent Road, Regent Terrace - from 13:30 hrs to 16:00 hrs on Saturday 28 June 2025 | Completed | City of Edinburgh Council | Waterloo Place (plus 3 more)
2025-06-28 | 28/06/2025 | 3843870 | CE006-L2727 | 1 |  | No | Event | Princes Street from The Mound to Leith Street; Waterloo Place in its entirety, Regent Road from Waterloo Place to Regent Terrace; Regent Terrace outside the United States Consulate | Stop the War Coalition March - Road Closures under Police Stop and Hold for a short period within stated times - Princes Street, Waterloo Place, Regent Road, Regent Terrace - from 13:30 hrs to 16:00 hrs on Saturday 28 June 2025 | Completed | City of Edinburgh Council | Waterloo Place (plus 3 more)
2025-06-19 20:00 | 26/06/2025 | 3692148 | CF014-S917382/1-BAU-EDI | 1 | Asset Activity and Reinstatement if Required | No | Standard | 135-139 | Build 1 xFW4 In Footway. Lay in 54m of 1 way duct (1 x 110mm) 44m F/W (FLAGS). Lay in 54m of 1 way duct (1 x 110mm) 44m F/W (FLAGS). Build 1 xFW4 In Footway | Closed | CityFibre Metro Networks Ltd | Princes Street
2025-06-23 00:10 | 25/06/2025 | 3840945 | CE003-S44971 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Tramway closure only required between Frederick Street and Castle Street westbound. | Tramway maintenance works. Overnight works. | Closed | City of Edinburgh Council | Princes Street
2025-06-21 00:15 | 21/06/2025 | 3785006 | SW100-NRSWA-10675/LWS-IW | 2 | Asset Activity and Reinstatement if Required | No | Major | On the carriageway at the junction with Frederick Street | Failed Scottish Water manhole reinstatement. Manhole sinking and carriageway breaking up | Closed | Scottish Water | Princes Street
2025-06-15 23:40 | 18/06/2025 | 3828350 | CE003-S44926 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | Castle St - Frederick St Eastbound - Tram Lane only - Lane 2 closure only of approx 50m lengths. | Welding and grinding of tramway rails from 23:40hrs to 04:30hrs | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-06-16 23:20 | 17/06/2025 | 3833208 | CE003-S44959 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Main carriageway both directions between South Charlotte Street and Lothian Road | Concrete repairs to tramway track form. Overnight works | Closed | City of Edinburgh Council | Princes Street
2025-06-15 23:05 | 16/06/2025 | 3833190 | CE003-S44958 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Main carriageway both directions between South Charlotte Street and Hanover Street | Concrete repairs to tramway track form. Overnight works | Closed | City of Edinburgh Council | Princes Street
2025-06-08 23:40 | 11/06/2025 | 3828343 | CE003-S44925 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | Castle St - Frederick St Eastbound - Tram Lane only - Lane 2 closure only of approx 50m lengths. | Welding and grinding of tramway rails from 23:40hrs to 04:30hrs | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-06-10 | 10/06/2025 | 3815043 | CE006-L2666 | 1 |  | No | Event | Corstorphine Road, Roseburn Terrace, West Coates, Haymarket Terrace, Haymarket, West Maitland Street, Shandwick Place, Princes Street, The Mound, North Bank Street, Bank Street , Lawnmarket, High Street, Canongate, Abbeyhill, Abbeymount, Montrose Terrace, London Road, Portobello Road, Piersfield Terrace, Moira Terrace, Portobello High Street, Abercorn Terrace, Joppa Road, Seaview Terrace, Eastfield. | Edinburgh Taxi Outing - Stop/Go Boards Traffic Control within the hours of 10:00 to 13:00 on 10 June 2025 with rolling closures for short periods within the times stated, implemented by Police Scotland. | Completed | City of Edinburgh Council | Corstorphine Road (plus 28 more)
2025-05-31 | 31/05/2025 | 3822171 | CE006-L2687 | 1 |  | Yes | Event | The Mound, From Mound Precinct west exit to Princes Street. Princes Street, From The Mound to Hanover Street. Hanover Street, From Princes Street to George Street. George Street, From Hanover Street to Charlotte Square. Charlotte Square, West leg from George Street to Charlotte Square north leg. Charlotte Square North leg in its entirety. | Support Palestine Event - Stop/Go Boards Traffic Control - The Mound, Princes Street, Hanover Street, George Street, Charlotte Square from 14:00hours to 16:00hours on 31 May 2025 | Abandoned | City of Edinburgh Council | The Mound (plus 4 more)
2025-05-28 09:42 | 28/05/2025 | 3824241 | SW100-NRSWA-12805/LWS-IW | 1 |  | No | Accepted Works | Westbound outside Costa Coffee at Waverley Mall | Sunken carriageway manhole | Accepted | Scottish Water | Princes Street
2025-05-26 00:15 | 28/05/2025 | 3816809 | CE003-S44924 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | East bound between South Charlotte Street and Frederick Street | Track works. Overnight works. | Closed | City of Edinburgh Council | Princes Street
2025-05-27 23:05 | 28/05/2025 | 3784173 | CE003-S44906 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Princes Street, Eastbound - Main carriageway | Concrete Repairs to track form and carriageway surfacing repairs | Closed | City of Edinburgh Council | Princes Street
2025-05-27 13:23 | 27/05/2025 | 3823673 | CE001-A66468 | 1 |  | No | Defective Apparatus | Westbound outside Costa Coffee at Waverley Mall | Sunken carriageway manhole | Accepted | City of Edinburgh Council | Princes Street
2025-05-24 | 26/05/2025 | 2920700 | SP202-2100709295B | 4 | Interim to Permanent Reinstatement | Yes | Major | FROM NO.31 TO JUNCTION OF | Remove TEMP Material and replace with new channel drains | Cleared | SP Energy Networks | Princes Street
2025-05-23 00:25 | 25/05/2025 | 3774483 | CE003-S44898 | 1 | Asset Activity and Reinstatement if Required | No | Standard | East bound between South Charlotte Street and Frederick Street | Track works. Overnight works. | Closed | City of Edinburgh Council | Princes Street
2025-05-22 07:00 | 23/05/2025 | 3820079 | CE017-S184 | 1 | Asset Activity and Reinstatement if Required | No | Urgent | At Junction Princes St@North Bridge | Emergency pole replacement | Closed | City of Edinburgh Council | Princes Street
2025-05-22 23:00 | 23/05/2025 | 3784142 | CE003-S44904 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Princes Street, Eastbound - Main carriageway, Lane 1 closure | Duct Chamber Cover Repair (CRCR) | Closed | City of Edinburgh Council | Princes Street
2025-05-22 00:55 | 22/05/2025 | 3774521 | CE003-S44899 | 1 | Asset Activity and Reinstatement if Required | No | Standard | West bound between Frederick Street and South Charlotte Street | Track works. Overnight works. | Closed | City of Edinburgh Council | Princes Street
2025-05-20 00:05 | 20/05/2025 | 3784183 | CE003-S44907 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Princes Street, both directions - Main carriageway, Lane 2 closures | Various concrete repairs to Tramway trackform | Closed | City of Edinburgh Council | Princes Street
2025-05-14 18:28 | 19/05/2025 | 3815741 | SP200-1166299S | 1 | Asset Activity and Reinstatement if Required | No | Emergency | O/S 129 | Excavate to repair LV fault | Closed | SP Energy Networks | Princes Street
2025-05-15 23:30 | 16/05/2025 | 3784529 | CE003-S44911 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Princes Street, Eastbound - Main carriageway, Lane 2 Closure | Concrete Patch repair | Closed | City of Edinburgh Council | Princes Street
2024-05-16 | 15/05/2025 | 3715215 | CE021-STARBUCKSCOFFEE5271 | 1 |  | No | Permission | 118, PRINCES STREET, PRINCES STREET, NEW TOWN, EDINBURGH, EH2 4AA | Starbucks Coffee - 527191 | Completed | City of Edinburgh Council | Princes Street
2025-05-12 22:30 | 13/05/2025 | 3784425 | CE003-S44909 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Princes Street, Westbound - Main carriageway | Concrete Repairs near the Mound | Closed | City of Edinburgh Council | Princes Street
2025-05-11 23:20 | 12/05/2025 | 3784409 | CE003-S44908 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Princes Street, both directions - Main carriageway, Lane 2 closures | Various concrete repairs to Tramway trackform | Closed | City of Edinburgh Council | Princes Street
2025-05-07 19:00 | 09/05/2025 | 3766682 | CE009-S64194 | 1 | Asset Activity and Reinstatement if Required | No | Remedial Other | At junction with Leith Street | Remedial works relating to resurfacing project LA 3246129 | Closed | City of Edinburgh Council | Princes Street
2025-04-26 | 26/04/2025 | 3801319 | CE006-L2626 | 1 |  | No | Temporary Traffic Restriction | The Mound, in it's entirety - Princes Street, from The Mound to Hanover Street - Hanover Street, from Princes Street to George Street - George Street, from Hanover Street to Charlotte Square - Charlotte Square, West leg from George Street to Charlotte Square North leg - Charlotte Square, North leg in it's entirety | Support Palestine – Stop/Go Boards Traffic Control – The Mound, Princes Street, Hanover Street, George Street, Charlotte Square – From 1400hrs to 1600hrs on Saturday 26th April 2025 | Completed | City of Edinburgh Council | The Mound (plus 4 more)
2025-04-26 | 26/04/2025 | 3801311 | CE006-L2625 | 1 |  | No | Event | The Mound, in it's entirety - Princes Street, from The Mound to Hanover Street - Hanover Street, from Princes Street to George Street - George Street, from Hanover Street to Charlotte Square - Charlotte Square, West leg from George Street to Charlotte Square North leg - Charlotte Square, North leg in it's entirety | Support Palestine – Stop/Go Boards Traffic Control – The Mound, Princes Street, Hanover Street, George Street, Charlotte Square – From 1400hrs to 1600hrs on Saturday 26th April 2025 | Completed | City of Edinburgh Council | The Mound (plus 4 more)
2025-04-21 | 23/04/2025 | 3779831 | GE001-GEO-S81-1246388 | 1 | Asset Activity and Reinstatement if Required | Yes | Minor With Excavation | Princes Street, West End, City of Edinburgh, Scotland, EH2 3DW | Knock and rebuild defective Zayo chamber in carriageway | Abandoned | Zayo | Princes Street
2025-04-21 00:15 | 22/04/2025 | 3785376 | CE003-S44913 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Princes St, Westbound between Frederick St and South Charlotte St | Track works | Closed | City of Edinburgh Council | Princes Street
2025-04-06 00:30 | 08/04/2025 | 3778391 | CE003-S44902 | 1 | Asset Activity and Reinstatement if Required | No | Standard | West bound between Frederick Street and South Charlotte Street | Tram track works. Overnight works. | Closed | City of Edinburgh Council | Princes Street
2025-04-01 | 04/04/2025 | 3786973 | CE003-S44918 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Princes Street, both directions - Main carriageway | Concrete and chamber cover repairs along the tram route | Closed | City of Edinburgh Council | Princes Street
2025-03-29 12:22 | 29/03/2025 | 3785006 | SW100-NRSWA-10675/LWS-IW | 1 |  | No | Accepted Works | On the carriageway at the junction with Frederick Street | Failed Scottish Water manhole reinstatement. Manhole sinking and carriageway breaking up | Accepted | Scottish Water | Princes Street
2025-03-25 12:05 | 27/03/2025 | 3781686 | GE001-GEO-S81-1246388EMRG | 1 | Asset Activity and Reinstatement if Required | No | Emergency | Princes Street, West End, City of Edinburgh, Scotland, EH2 3DW | Knock and rebuild defective Zayo chamber in carriageway - chamber collapsed causing a danger in the carriageway | Closed | Zayo | Princes Street
2025-03-26 16:39 | 26/03/2025 | 3783184 | CE001-A66282 | 1 |  | No | Defective Apparatus | On the carriageway at the junction with Frederick Street | Failed Scottish Water manhole reinstatement. Manhole sinking and carriageway breaking up | Accepted | City of Edinburgh Council | Princes Street
2025-03-10 00:30 | 12/03/2025 | 3713584 | SW100-NSW/PRINCESS/CLANCY | 1 | Asset Activity and Reinstatement if Required | Yes | Major | JUNCTION WITH FREDRICK STREET | CCTV - VACTORING - SURVEY WORKS | Abandoned | Scottish Water | Princes Street
2025-02-25 08:00 | 04/03/2025 | 3733627 | SP100-2101743565 | 1 | Asset Activity and Reinstatement if Required | No | Standard | O/S 131 | Excavate, backfill & reinstate jointbay to install new service and disconnect old | Closed | SP Energy Networks | Princes Street
2025-03-03 15:01 | 03/03/2025 | 3765469 | CE001-A66139 | 1 |  | No | Defective Apparatus | Carriageway westbound lane opposite South Charlotte Street | Sunken loose and noisy ZAYO manhole cover | Awaiting Response | City of Edinburgh Council | Princes Street
2025-03-03 11:21 | 03/03/2025 | 3765022 | SW100-3763381 | 1 |  | No | Accepted Works | On the carriageway at the junction with South St David Street | 2no sunken sv boxes | Accepted | Scottish Water | Princes Street
2025-02-27 14:24 | 27/02/2025 | 3763381 | CE001-A66133 | 1 |  | No | Defective Apparatus | On the carriageway at the junction with South St David Street | 2no sunken sv boxes | Accepted | City of Edinburgh Council | Princes Street
2025-02-19 | 26/02/2025 | 3714270 | SP200-826023F | 3 | Remedial Reinstatement | Yes | Remedial Other | O/S 78 | Reinstate modular LV fault | Closed | SP Energy Networks | Princes Street
2025-02-14 09:45 | 16/02/2025 | 3746712 | CE008-S1255 | 2 | Remedial Reinstatement | No | Remedial Other | Opposite Burger King in the inside lane at the pedestrian crossing | Collapsed gully | Closed | City of Edinburgh Council | Princes Street
2025-02-15 | 15/02/2025 | 3746293 | CE006-L2462 | 1 |  | No | Event | 1. Mound Place In its entirety. 2. The Mound In its entirety. 3. Princes Street From The Mound to Hanover Street. 4. Hanover Street From Princes Street to George Street. 5. George Street From Hanover Street to Charlotte Square. 6. Charlotte Square West leg from George Street to Charlotte Square north leg. 7. Charlotte Square North leg in its entirety. | Support Palestine public event. Stop/Go Boards Traffic Control from 13:00 to 15:00 on 15 February 2025 with a rolling closure for a short period within the times stated. | Completed | City of Edinburgh Council | Mound Place (plus 5 more)
2025-02-15 | 15/02/2025 | 3746332 | CE006-L2463 | 1 |  | No | Temporary Traffic Restriction | 1. Mound Place In its entirety. 2. The Mound In its entirety. 3. Princes Street From The Mound to Hanover Street. 4. Hanover Street From Princes Street to George Street. 5. George Street From Hanover Street to Charlotte Square. 6. Charlotte Square West leg from George Street to Charlotte Square north leg. 7. Charlotte Square North leg in its entirety. | Support Palestine public event. Stop/Go Boards Traffic Control from 13:00 to 15:00 on 15 February 2025 with a rolling closure for a short period within the times stated. | Completed | City of Edinburgh Council | Mound Place (plus 5 more)
2025-02-03 | 10/02/2025 | 3714270 | SP200-826023F | 2 | Remedial Reinstatement | Yes | Remedial Other | O/S 78 | Reinstate modular LV fault | Closed | SP Energy Networks | Princes Street
2025-02-05 08:33 | 06/02/2025 | 3740769 | CE019-S63896 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | footway | Install sign | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-02-04 15:31 | 04/02/2025 | 3746712 | CE008-S1255 | 1 | Asset Activity and Reinstatement if Required | No | Emergency | Opposite Burger King in the inside lane at the pedestrian crossing | Collapsed gully | Cleared | City of Edinburgh Council | Princes Street
2025-01-30 00:05 | 31/01/2025 | 3739935 | CE003-S44892 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Carriageway westbound at the Lothian Road junction | Concrete repairs to tramway track slab. Overnight works | Closed | City of Edinburgh Council | Princes Street
2025-01-29 | 31/01/2025 | 3739932 | CE003-S44891 | 1 | Asset Activity and Reinstatement if Required | Yes | Minor With Excavation | Carriageway westbound at the Lothian Road junction | Concrete repairs to tramway track slab. Overnight works | Abandoned | City of Edinburgh Council | Princes Street
2025-01-27 | 31/01/2025 | 2920700 | SP202-2100709295B | 3 | Interim to Permanent Reinstatement | Yes | Standard | FROM NO.31 TO JUNCTION OF | Remove TEMP Material and replace with new channel drains | Cleared | SP Energy Networks | Princes Street
2025-01-29 12:08 | 29/01/2025 | 3742853 | CE001-A66024 | 1 |  | No | Defective Apparatus | Eastbound carriageway before left turn onto Leith Street | Sunken and loose carriageway manhole | Denied | City of Edinburgh Council | Princes Street
2025-01-25 | 25/01/2025 | 3727589 | CE006-L2410 | 1 |  | No | Event | Mound Place in its entirety, The Mound in its entirety, Princes Street from The Mound to Hanover Street. Hanover Street from Princes Street to George Street, George Street from Hanover Street to Charlotte Square, Charlotte Square West leg from George Street to Charlotte Square north leg, Charlotte Square North leg in its entirety. | Support Palestine public event - Mound Place, The Mound, Princes Street, Hanover Street, George Street, Charlotte Square - Stop/Go Boards Traffic Control from 13:00 to 15:00 hrs on 25 January 2025 with a rolling closure for a short period within the times stated. | Completed | City of Edinburgh Council | Mound Place (plus 5 more)
2025-01-22 00:30 | 22/01/2025 | 3704451 | CE003-S44876 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | Westbound between Frederick Street and South St. David Street | Tram maintenance rail grinding. Overnight working. | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-01-21 00:30 | 21/01/2025 | 3704952 | CE003-S44878 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | Westbound between The Mound and South Charlotte Street | Tram maintenance rail grinding. Overnight works. | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-01-20 09:00 | 20/01/2025 | 3270007 | SP200-646569F | 2 | Remedial Reinstatement | No | Remedial Other | Outside no 99 Princes St | Change slab over and complete | Closed | SP Energy Networks | Princes Street
2025-01-20 00:30 | 20/01/2025 | 3704969 | CE003-S44879 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | Westbound between Lothian Road and Frederick Street | Tram maintenance rail grinding. Overnight works. | Closed No Excavation | City of Edinburgh Council | Princes Street
2025-01-18 | 18/01/2025 | 3727558 | CE006-L2406 | 1 |  | No | Event | Mound Place in its entirety, The Mound in its entirety, Princes Street from The Mound to Hanover Street, Hanover Street from Princes Street to George Street, George Street from Hanover Street to Charlotte Square, Charlotte Square west leg from George Street to Charlotte Square north leg, Charlotte Square North leg in its entirety. | Support Palestine public event. Stop/Go Boards Traffic Control from 13:00 to 15:00 on 18 January 2025 with a rolling closure for a short period within the times stated. | Completed | City of Edinburgh Council | Mound Place (plus 4 more)
2025-01-15 | 17/01/2025 | 3264138 | SP601-2101169842A | 2 | Remedial Reinstatement | Yes | Remedial Other | Opp No 75 | REMEDIAL PHASE - Remove Concrete and replace with new Caithness slabs | Closed | SP Energy Networks | Princes Street
2025-01-14 | 17/01/2025 | 3727041 | CE003-S44887 | 1 | Asset Activity and Reinstatement if Required | Yes | Remedial Other | Main carriageway between South St Andrew Street and Queensferry Street | Concrete repairs to tramway track slab. Overnight works. | Abandoned | City of Edinburgh Council | Princes Street
2024-12-23 12:10 | 06/01/2025 | 3723707 | SP200-585280R | 1 | Asset Activity and Reinstatement if Required | No | Emergency | O/S NO. 79 | EXCAVATE TO LV UG FAULT | Closed No Excavation | SP Energy Networks | Princes Street
2024-11-28 | 06/01/2025 | 3655017 | CE006-L2145 | 1 |  | No | Event | A8 (Princes St to Newbridge Roundabout), A90 (Queensferry Rd to junction with Headrig Rd), Inverleith Row, Montagu Terr, Howard St, Warriston Pl, Huntly St, Canonmills, Belford Rd, Queensferry Terr, Hamilton Pl, Henderson Row, Eyre Pl, Raeburn Pl, Kerr St, St Stephens St, Clarence St, West Silvermills Lane, Silvermills, Henderson Pl Lane, Henderson P, St Vincents Pl, Dundas St, Eyre Terr, Logan St, Eyre Pl Lane, Canon Lane, Canon St, Eyre Cres, Brandon St, Brandon Terr- in each road entirety | Winter Embargo 2024 – No Obstruction on C/W or F/W - A8 from Princes St to Newbridge Roundabout, A90 from Queensferry Road to junction with Headrig Road, Inverleith Row, Montagu Terrace, Howard Street, Warriston Place, Huntly Street, Canonmills, Belford Road, Queensferry Terrace, Hamilton Place, Henderson Row, Eyre Place, Raeburn Place, Kerr Street, St Stephens Street, Clarence Street, West Silvermills Lane, Silvermills, Henderson Place Lane, Henderson Place, St Vincents Place, Dundas Street, Eyre Terrace, Logan Street, Eyre Place Lane, Canon Lane, Canon Street, Eyre Crescent, Brandon Street, Brandon Terrace - in each road entirety from from 28 November 2024 to 6 January 2025 | Completed | City of Edinburgh Council | Princes Street (plus 45 more)
2024-11-28 | 06/01/2025 | 3655276 | CE006-L2149 | 1 |  | No | Event | see Description | Winter Embargo 2024 - No Obstruction on C/W or F/W - Abbey Mount, Abercromby Pl, Ainslie Pl, Antigua St, Atholl Pl, Bank St, Baxter's Pl, Belford Rd, Bellevue, Blair St, Bread St, Bristo Pl, Broughton St, Brunton Pl, Cadzow Pl, Castlehill, Chambers St, Charlotte Sq, Circus Pl, Clifton Terr, Coates Pl, Dean Bridge, Dewar Pl, Douglas Cres, Dundas St, Earl Grey St, East Fountainbridge, East London St, Easter Rd, Elm Row, Forrest Rd, Fountainbridge, Frederick St, George Iv Bridge, George St, Grassmarket, Greenside, Greyfriars Pl, Haddington Pl, Hanover St, Haymarket, High St, Holyrood Rd, Lady Lawson St, Leopold Pl, London St, Lothian Rd, Lynedoch Pl, Montrose Terr, North Bridge, North St Andrew St, Parliament Sq, Picardy Pl, Ponton St, Princes St, Queen St, Queen St Gdns East, Randolph Cliff, Regent Rd, Rutland Pl, Semple St, Shandwick Pl, South Bridge, South Charlotte St, South East Circus Pl, South St Andrew St, Spittal St, St Andrew Sq, St Colme St, St Mary's St, Telford Rd, The Mound, Torphichen Pl, Union Pl, Waterloo Pl, Waverley Bridge, West Maitland St, West Port, York Pl - in each road entirety from 28 November 2024 to 6 January 2025 | Completed | City of Edinburgh Council | North Bridge (plus 58 more)
2024-12-06 12:13 | 24/12/2024 | 3714270 | SP200-826023F | 1 | Asset Activity and Reinstatement if Required | No | Emergency | O/S 78 | Excavate to repair LV fault | Closed | SP Energy Networks | Princes Street
2024-12-20 07:30 | 20/12/2024 | 3289148 | SP200-836143S | 2 | Interim to Permanent Reinstatement | No | Minor With Excavation | O/S 42 | Make interim reinstatement permanent - Excavate to repair LV Fault | Closed | SP Energy Networks | Princes Street
2024-11-28 07:30 | 28/11/2024 | 3557264 | SP200-1002367S | 3 | Interim to Permanent Reinstatement | No | Minor With Excavation | O/S 2 | **Perm Phase** Complete new slab | Closed | SP Energy Networks | Princes Street
2024-11-24 08:30 | 24/11/2024 | 3668195 | SW100-2611080/CLANCY | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Meter location "M1 on footpath .5mtr side of bus stop in front of hotel entrance XY: 325152, 673832 | External Exchange Meter | Closed | Scottish Water | Princes Street
2024-11-07 07:30 | 07/11/2024 | 3070795 | SP200-668623S | 2 | Remedial Reinstatement | No | Remedial Other | O/S 130 | REMEDIAL PHASE - In order to relay broken slabs | Closed | SP Energy Networks | Princes Street
2024-11-05 15:38 | 05/11/2024 | 3693974 | CE001-A65765 | 1 |  | No | Defective Apparatus | At bus stop PK outside 53 | Sunken footway manhole | Awaiting Response | City of Edinburgh Council | Princes Street
2024-10-27 22:00 | 01/11/2024 | 3679074 | CE003-S44870 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Main carriageway both directions between Lothian Road and South St David Street. | Concrete repairs to tramway track slab. Nightshift working. | Closed | City of Edinburgh Council | Princes Street
2024-10-31 07:30 | 31/10/2024 | 3307743 | SP100-2100722119 | 2 | Remedial Reinstatement | No | Remedial Other | 0/S 100 | **Remedial Phase** To repair broken slabs | Closed | SP Energy Networks | Princes Street
2024-10-28 12:50 | 28/10/2024 | 3345647 | SP200-865909S/A | 2 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | O/S NO.99 | **Perm Phase** Complete mason work to permanent finish | Closed | SP Energy Networks | Princes Street
2024-10-28 | 28/10/2024 | 3557264 | SP200-1002367S | 2 | Interim to Permanent Reinstatement | Yes | Minor With Excavation | O/S 2 | **Perm Phase** Complete new slab | Cleared | SP Energy Networks | Princes Street
2024-10-12 | 12/10/2024 | 3566256 | SW100-08613199/LWS-IW | 3 | Asset Activity and Reinstatement if Required | No | Major | At the junction with South St David Street | 2 no sunken SV boxes | Closed No Excavation | Scottish Water | Princes Street
2024-10-12 | 12/10/2024 | 3675821 | CE006-L2259/TRO1 | 1 |  | No | Temporary Traffic Restriction | The Mound Precinct in its entirety, The Mound from Mound Precinct south access to Market St, Market St from The Mound to Waverley Bridge, Waverley Bridge in its entirety, Princes St from Waverley Bridge to South St David St, South St David St its entirety, George St from South St David St to Hanover St, Hanover St from George St to Princes St, Princes Street from Hanover St to The Mound, The Mound from Princes St to Mound Precinct south access | Support Palestine - Stop/ Go Boards Traffic Control - The Mound Precinct, The Mound, Market Street, Waverley Bridge, Princes Street, South St David Street, George Street, Hanover Street - from 13:00 hrs to 15:00 hrs on 12 October 2024 | Completed | City of Edinburgh Council | The Mound (plus 6 more)
2024-10-12 | 12/10/2024 | 3675813 | CE006-L2259 | 1 |  | No | Event | The Mound Precinct in its entirety, The Mound from Mound Precinct south access to Market St, Market St from The Mound to Waverley Bridge, Waverley Bridge in its entirety, Princes St from Waverley Bridge to South St David St, South St David St its entirety, George St from South St David St to Charlotte Square, Charlotte Square east leg from George Street to Charlotte Square north leg, Charlotte Square north leg in its entirety. | Support Palestine - Stop/ Go Boards Traffic Control - The Mound Precinct, The Mound, Market Street, Waverley Bridge, Princes Street, South St David Street, George Street, Charlotte Square - from 12:00 hrs to 14:00 hrs on 12 October 2024 | Completed | City of Edinburgh Council | The Mound (plus 4 more)
2024-10-05 | 05/10/2024 | 3668392 | CE006-L2229 | 1 |  | No | Event | The Mound Precinct in its entirety. The Mound from Mound Precinct south access to Market Street. Market Street from The Mound to Waverley Bridge. Waverley Bridge In its entirety. Princes Street from Waverley Bridge to South St David Street. South St David Street in its entirety. George Street from South St David Street to Hanover Street. Hanover Street from George Street to Princes Street. Princes Street from Hanover Street to The Mound. | Support Palestine public event. Stop/Go Boards Traffic Control from 13:00hrs to 15:00hrs with a rolling closure for a short period within the times stated on 5 October 2024. | Completed | City of Edinburgh Council | The Mound (plus 6 more)
2024-10-05 | 05/10/2024 | 3668403 | CE006-L2230 | 1 |  | No | Temporary Traffic Restriction | The Mound Precinct in its entirety. The Mound from Mound Precinct south access to Market Street. Market Street from The Mound to Waverley Bridge. Waverley Bridge In its entirety. Princes Street from Waverley Bridge to South St David Street. South St David Street in its entirety. George Street from South St David Street to Hanover Street. Hanover Street from George Street to Princes Street. Princes Street from Hanover Street to The Mound. | Support Palestine public event. Stop/Go Boards Traffic Control from 13:00hrs to 15:00hrs with a rolling closure for a short period within the times stated on 5 October 2024. | Completed | City of Edinburgh Council | The Mound (plus 6 more)
2024-10-03 22:00 | 04/10/2024 | 3649810 | CE003-S44853 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Carriageway between Hanover Street and South St David Street | Concrete and chamber cover repairs. Nightshift working. | Closed | City of Edinburgh Council | Princes Street
2024-10-03 22:00 | 04/10/2024 | 3649811 | CE003-S44854 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Carriageway between Hanover Street and South St David Street | Concrete and chamber cover repairs. Nightshift working. | Closed | City of Edinburgh Council | Princes Street
2024-10-02 08:00 | 03/10/2024 | 3242204 | SP200-801019S | 2 | Remedial Reinstatement | No | Remedial Other | o/s no. 99 | **REMEDIAL PHASE** - Complete new slab | Closed | SP Energy Networks | Princes Street
2024-09-16 09:30 | 26/09/2024 | 3639021 | CE019-S63800 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Footway o/s No 53 | Install sign pole | Cleared | City of Edinburgh Council | Princes Street
2024-09-20 | 24/09/2024 | 3566256 | SW100-08613199/LWS-IW | 2 | Asset Activity and Reinstatement if Required | Yes | Minor With Excavation | At the junction with South St David Street | 2 no sunken SV boxes | Accepted | Scottish Water | Princes Street
2024-09-12 14:32 | 20/09/2024 | 3660328 | SW100-CSW1209/1/CLANCY | 1 | Asset Activity and Reinstatement if Required | No | Emergency | junction with fredrick street | take cover / rebuild chamber | Closed | Scottish Water | Princes Street
2024-09-16 20:00 | 18/09/2024 | 3661169 | CE008-S984 | 1 | Asset Activity and Reinstatement if Required | No | Urgent | At the junction of Princes Street and Frederick Street. | Carriageway Resurfacing Works- nightshift from 20:00 – 04:30 | Closed | City of Edinburgh Council | Princes Street
2024-09-12 23:20 | 13/09/2024 | 3649788 | CE003-S44852 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Carriageway between Lothian Road and Waverley Bridge | Concrete and chamber cover repairs. Nightshift working. | Closed | City of Edinburgh Council | Princes Street
2024-09-10 23:25 | 11/09/2024 | 3649758 | CE003-S44850 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Carriageway between Lothian Road and South Charlotte Street | Concrete and chamber cover repairs. Nightshift working. | Closed | City of Edinburgh Council | Princes Street
2024-07-27 | 01/09/2024 | 3579202 | CE006-L1761 | 1 |  | No | Event | A8 (Princes St to Newbridge Roundabout), A90 (Queensferry Rd to junction with Headrig Rd), Inverleith Row, Montagu Terr, Howard St, Warriston Pl, Huntly St, Canonmills, Belford Rd, Queensferry Terr, Hamilton Pl, Henderson Row, Eyre Pl, Raeburn Pl, Kerr St, St Stephens St, Clarence St, West Silvermills Lane, Silvermills, Henderson Pl Lane, Henderson P, St Vincents Pl, Dundas St, Eyre Terr, Logan St, Eyre Pl Lane, Canon Lane, Canon St, Eyre Cres, Brandon St, Brandon Terr- in each road entirety | Summer Embargo 2024 – No Obstruction on C/W or F/W - A8 from Princes St to Newbridge Roundabout, A90 from Queensferry Road to junction with Headrig Road, Inverleith Row, Montagu Terrace, Howard Street, Warriston Place, Huntly Street, Canonmills, Belford Road, Queensferry Terrace, Hamilton Place, Henderson Row, Eyre Place, Raeburn Place, Kerr Street, St Stephens Street, Clarence Street, West Silvermills Lane, Silvermills, Henderson Place Lane, Henderson Place, St Vincents Place, Dundas Street, Eyre Terrace, Logan Street, Eyre Place Lane, Canon Lane, Canon Street, Eyre Crescent, Brandon Street, Brandon Terrace - in each road entirety from 27 July 2024 to 1 September 2024 | Completed | City of Edinburgh Council | Princes Street (plus 45 more)
2024-07-27 | 01/09/2024 | 3579261 | CE006-L1766 | 1 |  | No | Event | see Description | Summer Embargo 2024 - No Obstruction on C/W or F/W - Abbey Mount, Abercromby Pl, Ainslie Pl, Antigua St, Atholl Pl, Bank St, Baxter's Pl, Belford Rd, Bellevue, Blair St, Bread St, Bristo Pl, Broughton St, Brunton Pl, Cadzow Pl, Castlehill, Chambers St, Charlotte Sq, Circus Pl, Clifton Terr, Coates Pl, Dean Bridge, Dewar Pl, Douglas Cres, Dundas St, Earl Grey St, East Fountainbridge, East London St, Easter Rd, Elm Row, Forrest Rd, Fountainbridge, Frederick St, George Iv Bridge, George St, Grassmarket, Greenside, Greyfriars Pl, Haddington Pl, Hanover St, Haymarket, High St, Holyrood Rd, Lady Lawson St, Leopold Pl, London St, Lothian Rd, Lynedoch Pl, Montrose Terr, North Bridge, North St Andrew St, Parliament Sq, Picardy Pl, Ponton St, Princes St, Queen St, Queen St Gdns East, Randolph Cliff, Regent Rd, Rutland Pl, Semple St, Shandwick Pl, South Bridge, South Charlotte St, South East Circus Pl, South St Andrew St, Spittal St, St Andrew Sq, St Colme St, St Mary's St, Telford Rd, The Mound, Torphichen Pl, Union Pl, Waterloo Pl, Waverley Bridge, West Maitland St, West Port, York Pl - in each road entirety from 27 July 2024 to 1 September 2024 | Completed | City of Edinburgh Council | North Bridge (plus 58 more)
2024-07-04 23:00 | 05/07/2024 | 3596395 | CE003-S44827 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Main carriageway eastbound lanes 2 and 3 | Concrete and chamber cover repairs. Overnight works 11:25pm until 4:30am. | Closed | City of Edinburgh Council | Princes Street
2024-07-02 23:00 | 03/07/2024 | 3596191 | CE003-S44823 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Main carriageway both directions | Concrete and chamber cover repairs. Overnight works 10:30pm until 4.30am. | Closed | City of Edinburgh Council | Princes Street
2024-07-01 23:00 | 02/07/2024 | 3596113 | CE003-S44822 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Main carriageway both directions | Concrete and chamber cover repairs. Overnight works 11:30pm until 4.30am. | Closed | City of Edinburgh Council | Princes Street
2024-06-30 22:30 | 01/07/2024 | 3596110 | CE003-S44821 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Main carriageway eastbound | Concrete and chamber cover repairs. Overnight works 10:30pm until 4.30am. | Closed | City of Edinburgh Council | Princes Street
2024-06-28 23:30 | 29/06/2024 | 3481594 | SW100-08465514/LWS-IW | 2 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Westbound lane next to the Scott Monument | 2 sunken SV boxes | Closed | Scottish Water | Princes Street
2024-06-28 00:10 | 28/06/2024 | 3596051 | CE003-S44820 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Main carriageway westbound at Lothian Road junction | Concrete and chamber cover repairs. Overnight works 11:59pm until 5am. | Closed | City of Edinburgh Council | Princes Street
2024-06-26 23:45 | 27/06/2024 | 3596036 | CE003-S44819 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Main carriageway both directions | Concrete and chamber cover repairs. Overnight works 11:30pm until 5am. | Closed | City of Edinburgh Council | Princes Street
2024-06-11 | 11/06/2024 | 3592084 | CE006-L1880 | 1 |  | No | Temporary Traffic Restriction | Corstorphine Road, Roseburn Terrace, West Coates, Haymarket Terrace, Haymarket, West Maitland Street, Shandwick Place, Princes Street, The Mound, North Bank Street, Bank Street , Lawnmarket, High Street, Canongate, Abbeyhill, Abbeymount, Montrose Terrace, London Road, Portobello Road, Piersfield Terrace, Moira Terrace, Portobello High Street, Abercorn Terrace, Joppa Road, Seaview Terrace, Eastfield | Edinburgh Children's Taxi Trade Outing - Stop/ Go Boards Traffic Control - ‘rolling closures’ for short period within hours of 10:00 to 13:00 hrs on 11 June 2024 | Completed | City of Edinburgh Council | Corstorphine Road (plus 28 more)
2024-06-11 | 11/06/2024 | 3592067 | CE006-L1879 | 1 |  | No | Event | Corstorphine Road, Roseburn Terrace, West Coates, Haymarket Terrace, Haymarket, West Maitland Street, Shandwick Place, Princes Street, The Mound, North Bank Street, Bank Street , Lawnmarket, High Street, Canongate, Abbeyhill, Abbeymount, Montrose Terrace, London Road, Portobello Road, Piersfield Terrace, Moira Terrace, Portobello High Street, Abercorn Terrace, Joppa Road, Seaview Terrace, Eastfield | Edinburgh Children's Taxi Trade Outing - Stop/ Go Boards Traffic Control - ‘rolling closures’ for short period within hours of 10:00 to 13:00 hrs on 11 June 2024 | Completed | City of Edinburgh Council | Corstorphine Road (plus 28 more)
2024-06-02 00:29 | 03/06/2024 | 3525312 | CE003-S44742 | 1 | Asset Activity and Reinstatement if Required | No | Major | Eastbound between Hanover Street and Frederick Street | Joint sealant works. Overnight working. | Closed No Excavation | City of Edinburgh Council | Princes Street
2024-05-22 00:15 | 24/05/2024 | 3525288 | CE003-S44741 | 1 | Asset Activity and Reinstatement if Required | No | Major | Westbound between Hanover Street and South St David Street | Joint sealant works. Overnight working. | Closed No Excavation | City of Edinburgh Council | Princes Street
2024-05-21 21:00 | 22/05/2024 | 3587647 | CE009-S63972 | 1 | Asset Activity and Reinstatement if Required | No | Urgent | Eastbound carriageway in the left turn lane at Leith Street | Collapsed frame and cover | Closed | City of Edinburgh Council | Princes Street
2024-05-20 00:20 | 21/05/2024 | 3525258 | CE003-S44740 | 1 | Asset Activity and Reinstatement if Required | No | Major | Westbound between South St Andrew Street and South St David Street | Joint sealant works. Overnight working. | Closed No Excavation | City of Edinburgh Council | Princes Street
2024-05-18 | 18/05/2024 | 3582824 | CE006-L1797 | 1 |  | No | Temporary Traffic Restriction | Waverley Bridge in its entirety, Princes Street Westbound between Waverley Bridge and South St David St, South St David Street from Princes St to George St, George Street from South St David St to Hanover St, Hanover Street from George St to Princes St; The Mound, North Bank Street and Bank Street in each road entirety, Lawnmarket from George IV Bridge to High St; High Street, Canongate and Horse Wynd in each road entirety; Queens Drive from Horse Wynd to roundabout at Broad Pavement car park | Commemorate Palestinian Nakba March - No Obstruction on C/W or F/W - from 12:30 hrs to 16:00 hrs on Saturday 18 May 2024 | Completed | City of Edinburgh Council | Waverley Bridge (plus 13 more)
2024-05-18 | 18/05/2024 | 3582814 | CE006-L1796 | 1 |  | No | Event | Waverley Bridge in its entirety, Princes Street Westbound between Waverley Bridge and South St David St, South St David Street from Princes St to George St, George Street from South St David St to Hanover St, Hanover Street from George St to Princes St; The Mound, North Bank Street and Bank Street in each road entirety, Lawnmarket from George IV Bridge to High St; High Street, Canongate and Horse Wynd in each road entirety; Queens Drive from Horse Wynd to roundabout at Broad Pavement car park | Commemorate Palestinian Nakba March - No Obstruction on C/W or F/W - from 12:30 hrs to 16:00 hrs on Saturday 18 May 2024 | Completed | City of Edinburgh Council | Waverley Bridge (plus 13 more)
2024-04-04 05:16 | 19/04/2024 | 3557264 | SP200-1002367S | 1 | Asset Activity and Reinstatement if Required | No | Emergency | O/S 2 | Excavate to repair LV fault | Cleared | SP Energy Networks | Princes Street
2024-04-18 09:49 | 18/04/2024 | 3566256 | SW100-08613199/LWS-IW | 1 |  | No | Accepted Works | At the junction with South St David Street | 2 no sunken SV boxes | Accepted | Scottish Water | Princes Street
2024-04-17 15:11 | 17/04/2024 | 3565971 | CE001-A65178 | 1 |  | No | Defective Apparatus | At the junction with South St David Street | 2 no sunken SV boxes | Accepted | City of Edinburgh Council | Princes Street
2024-04-01 17:50 | 16/04/2024 | 3349570 | SP202-2101286497/1SB | 1 | Asset Activity and Reinstatement if Required | No | Standard | o/s 2 | Excavate to Replace link box | Closed No Excavation | SP Energy Networks | Princes Street
2024-04-12 19:00 | 16/04/2024 | 3051043 | TE003-VM/CIP/414844 | 4 | Asset Activity and Reinstatement if Required | Yes | Minor With Excavation | o/s Balmoral Hotel on carriageway | Manhole cover damaging surround. | Accepted | Virgin Media Limited | Princes Street
2024-04-12 19:00 | 13/04/2024 | 3051043 | TE003-VM/CIP/414844 | 5 | Asset Activity and Reinstatement if Required | Yes | Minor With Excavation | o/s Balmoral Hotel on carriageway | Manhole cover damaging surround. | Accepted | Virgin Media Limited | Princes Street
2024-04-09 11:45 | 09/04/2024 | 3560070 | CE001-U61695 | 1 |  | No | Unattributable Works | At bus stop PK | Utility Works by Morrisons Utilities#, causing defective reinstatement of x7 450x450 perfectas | Accepted | City of Edinburgh Council | Princes Street
2024-04-09 11:32 | 09/04/2024 | 3560044 | CE001-U61694 | 1 |  | No | Unattributable Works | Outside 120b | Utility works carried out by Morrisons Utility, causing 1 rocking 450x450 slab | Accepted | City of Edinburgh Council | Princes Street
2024-04-06 00:30 | 06/04/2024 | 3002226 | SW100-07753102/LWS-IW | 2 | Asset Activity and Reinstatement if Required | No | Major | At the junction of South St David Street on the eastbound carriageway. | Loose and noisy manhole. | Closed | Scottish Water | Princes Street
2024-04-04 23:30 | 05/04/2024 | 3527800 | CE003-S44794 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Princes Street Eastbound (South Charlotte St Junction) Lane 3 Closure | Concrete and Chamber Cover repairs Nightshift road closure from 11:30pm until 4:45am, Nightshift only. Machine excavations. Tram gate system in place during tram hours. | Closed | City of Edinburgh Council | Princes Street
2024-04-03 23:33 | 04/04/2024 | 3527795 | CE003-S44793 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Eastbound main carriageway | Concrete and Chamber Cover repairs Nightshift road closure from 10pm until 4:30am, Nightshift only. Machine excavations. Tram gate system in place during tram hours. | Closed | City of Edinburgh Council | Princes Street
2024-04-02 09:30 | 04/04/2024 | 3051043 | TE003-VM/CIP/414844 | 2 | Asset Activity and Reinstatement if Required | Yes | Minor With Excavation | o/s Balmoral Hotel on carriageway | Manhole cover damaging surround. | Accepted | Virgin Media Limited | Princes Street
2024-04-02 19:00 | 04/04/2024 | 3051043 | TE003-VM/CIP/414844 | 3 | Asset Activity and Reinstatement if Required | Yes | Minor With Excavation | o/s Balmoral Hotel on carriageway | Manhole cover damaging surround. | Accepted | Virgin Media Limited | Princes Street
2024-03-07 00:46 | 02/04/2024 | 3540205 | SP200-992893S | 1 | Asset Activity and Reinstatement if Required | No | Emergency | o/s no 54 | Excavate to repair l/v fault.Vulnerable customers may be impacted by these works, hence why they have been raised under the Emergency Notice type. Should you require further information, please contact Reporting@spenergynetworks.co.uk | Closed | SP Energy Networks | Princes Street
2024-04-02 00:30 | 02/04/2024 | 3526757 | CE003-S44771 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | West Bound | Road Markings Renewals. Overnight working | Closed No Excavation | City of Edinburgh Council | Princes Street
2024-04-02 00:28 | 02/04/2024 | 3526756 | CE003-S44770 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | East Bound | Road Markings Renewals. Overnight working | Closed No Excavation | City of Edinburgh Council | Princes Street
2024-04-01 00:30 | 01/04/2024 | 3526755 | CE003-S44769 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | West Bound | Road Markings Renewals. Overnight working | Closed No Excavation | City of Edinburgh Council | Princes Street
2024-04-01 00:30 | 01/04/2024 | 3526754 | CE003-S44768 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | East Bound | Road Markings Renewals. Overnight working | Closed No Excavation | City of Edinburgh Council | Princes Street
2024-03-26 23:45 | 27/03/2024 | 3527715 | CE003-S44790 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Westbound main carriageway | Concrete and Chamber Cover repairs Nightshift road closure from 10pm until 4:30am, Nightshift only. Machine excavations. Tram gate system in place during tram hours. | Closed | City of Edinburgh Council | Princes Street
2024-03-21 00:18 | 21/03/2024 | 3526751 | CE003-S44765 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | West Bound | Road Markings Renewals. Overnight working | Closed No Excavation | City of Edinburgh Council | Princes Street
2024-03-19 23:59 | 20/03/2024 | 3526603 | CE003-S44758 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | West Bound | Road Markings Renewals. Overnight working | Closed No Excavation | City of Edinburgh Council | Princes Street
2024-03-19 16:00 | 19/03/2024 | 2850944 | SW100-1274278/CLANCY | 5 | Remedial Reinstatement | No | Remedial Other | No 20 | Remedial works | Closed | Scottish Water | Princes Street
2024-03-19 00:30 | 19/03/2024 | 3526671 | CE003-S44761 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | East Bound | Road Markings Renewals. Overnight working | Closed No Excavation | City of Edinburgh Council | Princes Street
2024-03-18 00:03 | 18/03/2024 | 3526476 | CE003-S44755 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | East Bound | Road Markings Renewals. Overnight working | Closed No Excavation | City of Edinburgh Council | Princes Street
2024-03-15 23:30 | 16/03/2024 | 3420294 | SW100-08378049/LWS-IW | 2 | Asset Activity and Reinstatement if Required | No | Major | Eastbound lane at junction with Frederick Street | Badly sunken and rocking manhole. | Closed | Scottish Water | Princes Street
2024-03-12 11:00 | 15/03/2024 | 3409880 | SW100-08360165/LWS-IW | 3 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | Outside Hotel Indigo | Low water toby on footway. | Closed | Scottish Water | Princes Street
2024-03-12 09:40 | 13/03/2024 | 3510973 | SP700-2101507502/3 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | 25-10 | Removal of 2 inspection chambers | Closed | SP Energy Networks | Princes Street
2024-03-11 00:05 | 11/03/2024 | 3510834 | SP700-2101507502/A2 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | O/S 40 | Removal of 4 inspection chambers on Princes Street between 46 and 30. | Closed | SP Energy Networks | Princes Street
2024-03-08 07:00 | 08/03/2024 | 3540140 | CE009-S63903 | 1 | Asset Activity and Reinstatement if Required | No | Urgent | Westbound lane outside Balmoral Hotel | Utility frame and cover repairs | Closed | City of Edinburgh Council | Princes Street
2024-03-01 00:10 | 08/03/2024 | 3510817 | SP700-2101507502/2 | 1 | Asset Activity and Reinstatement if Required | No | Standard | 77-47 | Removal of 17 inspection chambers | Closed | SP Energy Networks | Princes Street
2024-03-06 19:00 | 06/03/2024 | 3527290 | TE001-NNERBU-CX00083757 | 1 | Asset Activity and Reinstatement if Required | No | Minor Without Excavation | 1 and 3 Princes Street, Edinburgh EH2 2AN | DESILT TO CLEAR CHAMBER BLOCKAGE- NO EXCAVATION | Closed No Excavation | Virgin Media Limited | Princes Street
2024-02-28 00:20 | 28/02/2024 | 3510778 | SP700-2101507502/A1 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | O/S 80 | Removal of 1 inspection chambers on Princes Street between 98 and 78. | Closed | SP Energy Networks | Princes Street
2024-02-27 00:12 | 27/02/2024 | 3510768 | SP700-2101507502/1 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | 117-99 | Removal of 19 inspection chambers | Closed | SP Energy Networks | Princes Street
2024-02-19 23:20 | 26/02/2024 | 3512769 | SP700-2101507502/B | 1 | Asset Activity and Reinstatement if Required | No | Standard | between 134 and 118 | excavate for removal of 19 inspection chambers on Princes Street | Closed | SP Energy Networks | Princes Street
2024-02-19 09:25 | 19/02/2024 | 3509503 | SP700-2101507502 | 1 | Asset Activity and Reinstatement if Required | No | Minor With Excavation | O/S 135 - 147 | Excavation for removal of 5 inspection chambers. | Closed | SP Energy Networks | Princes Street
2024-02-05 16:00 | 07/02/2024 | 3494751 | TE001-NNERMA-CX00082094 | 1 | Asset Activity and Reinstatement if Required | No | Standard | Waverley Rail Station, WAVERLEY BRIDGE, OLD TOWN, EDINBURGH, EH1 1BQ | CIVILS TIE IN TO OPENREACH PIA NETWORK REQUIRED | Closed | Virgin Media Limited | Princes Street
2024-01-15 | 17/01/2024 | 2518520 | SP100-612965351 | 7 | Remedial Reinstatement | Yes | Remedial Other | opposite 130 beside statue | Remedial works re replacement of broken slabs. | Closed | SP Energy Networks | Princes Street
2024-01-15 | 17/01/2024 | 2518520 | SP100-612965351 | 6 | Remedial Reinstatement | Yes | Remedial Other | opposite 130 beside statue | Remedial works re replacement of broken slabs. | Closed | SP Energy Networks | Princes Street
2024-01-10 | 12/01/2024 | 3409880 | SW100-08360165/LWS-IW | 2 | Asset Activity and Reinstatement if Required | Yes | Minor With Excavation | Outside Hotel Indigo | Low water toby on footway. | Accepted | Scottish Water | Princes Street
2023-11-23 | 08/01/2024 | 3424080 | CE006-L1285 | 1 |  | No | Event | A8 (Princes St to Newbridge Roundabout), A90 (Queensferry Rd to junction with Headrig Rd), Inverleith Row, Montagu Terr, Howard St, Warriston Pl, Huntly St, Canonmills, Belford Rd, Queensferry Terr, Hamilton Pl, Henderson Row, Eyre Pl, Raeburn Pl, Kerr St, St Stephens St, Clarence St, West Silvermills Lane, Silvermills, Henderson Pl Lane, Henderson P, St Vincents Pl, Dundas St, Eyre Terr, Logan St, Eyre Pl Lane, Canon Lane, Canon St, Eyre Cres, Brandon St, Brandon Terr- in each road entirety | Winter Embargo 2023 – No Obstruction on C/W or F/W - A8 from Princes St to Newbridge Roundabout, A90 from Queensferry Road to junction with Headrig Road, Inverleith Row, Montagu Terrace, Howard Street, Warriston Place, Huntly Street, Canonmills, Belford Road, Queensferry Terrace, Hamilton Place, Henderson Row, Eyre Place, Raeburn Place, Kerr Street, St Stephens Street, Clarence Street, West Silvermills Lane, Silvermills, Henderson Place Lane, Henderson Place, St Vincents Place, Dundas Street, Eyre Terrace, Logan Street, Eyre Place Lane, Canon Lane, Canon Street, Eyre Crescent, Brandon Street, Brandon Terrace - in each road entirety from 23 November 2023 to 8 January 2024 | Completed | City of Edinburgh Council | Princes Street (plus 44 more)
2023-11-23 | 08/01/2024 | 3424268 | CE006-L1289 | 1 |  | No | Event | see Description | Winter Embargo 2023 - No Obstruction on C/W or F/W - Abbey Mount, Abercromby Pl, Ainslie Pl, Antigua St, Atholl Pl, Bank St, Baxter's Pl, Belford Rd, Bellevue, Blair St, Bread St, Bristo Pl, Broughton St, Brunton Pl, Cadzow Pl, Castlehill, Chambers St, Charlotte Sq, Circus Pl, Clifton Terr, Coates Pl, Dean Bridge, Dewar Pl, Douglas Cres, Dundas St, Earl Grey St, East Fountainbridge, East London St, Easter Rd, Elm Row, Forrest Rd, Fountainbridge, Frederick St, George Iv Bridge, George St, Grassmarket, Greenside, Greyfriars Pl, Haddington Pl, Hanover St, Haymarket, High St, Holyrood Rd, Lady Lawson St, Leopold Pl, London St, Lothian Rd, Lynedoch Pl, Montrose Terr, North Bridge, North St Andrew St, Parliament Sq, Picardy Pl, Ponton St, Princes St, Queen St, Queen St Gdns East, Randolph Cliff, Regent Rd, Rutland Pl, Semple St, Shandwick Pl, South Bridge, South Charlotte St, South East Circus Pl, South St Andrew St, Spittal St, St Andrew Sq, St Colme St, St Mary's St, Telford Rd, The Mound, Torphichen Pl, Union Pl, Waterloo Pl, Waverley Bridge, West Maitland St, West Port, York Pl - in each road entirety from 23 November 2023 to 8 January 2024 | Completed | City of Edinburgh Council | North Bridge (plus 58 more)